## Sprint1.1 (hidden)
Epic | Story | JiRA ID | Subtask | Effort (hrs.) | Assignee | Remarks | New Remarks
Call Recording Migration | [7 empty] | Name | Number of working days | Leaves | Total Effort (7h/d) | Planned Effort | Available Effort
| N22 Migration | UGV-3479 | PreConfiguration Checklist | 12 |  | Gopal |  | Asim | 9 | 0 | 63 | 18 | 45
|  | UGV-3480 | Automation Setup PBX and ECC | 8 |  | Hardik |  | Deevena | 9 | 7 | 14 | 55 | -41
|  | UGV-3481 | Customer Account Identification | 3 |  | Asim |  | Hardik | 9 | 0 | 63 | 69 | -6
|  | UGV-3482 | Customer Account Data Collection-1 | 8 |  | Asim |  | Himanshu | 9 | 1 | 33.6 | 14 | 19.6
|  | UGV-3483 | Customer Account Data Collection-2 | 8 |  | Gopal |  | Gopal | 9 | 0 | 63 | 41 | 22
|  | UGV-3484 | Automation Setup BOSS | 2 |  | Himanshu |  | Mohit | 6 | 2 | 28 | 20 | 8
|  | UGV-3485 | Price Plan Validation and Trial Orders | 1.5 |  | Asim |  | Neha | 9 | 3 | 42 | 41 | 1
|  | UGV-3486 | PBX Manual Validation | 4 |  | Hardik |  | Sandeep | 9 | 0 | 63 | 56 | 7
|  | UGV-3487 | Pre Migration ITSM -1 | 6 |  | Asim |  | Soumya | 5 | 2 | 21 | 16 | 5
|  | UGV-3488 | Pre Migration ITSM -2 | 6 |  | Gopal |  | Total | 74 | 15 | 390.6 | 330 | 60.6
|  | UGV-3489 | Pre Migration Automation Tasks | 6 |  | Himanshu |  |  |  |  | 55.8
|  | UGV-3490 | Cutover ITSM BOSS-1 | 4 |  | Asim
|  | UGV-3491 | Cutover ITSM BOSS-2 | 4 |  | Gopal
|  | UGV-3492 | Cutover ITSM PBX-1 | 1.5 |  | Hardik
|  | UGV-3493 | Cutover ITSM PBX-2 | 1.5 |  | Deevena
|  | UGV-3494 | Billing ITSM Validation | 3 |  | Asim
|  | UGV-3495 | Automation Execution | 6 |  | Himanshu
|  | UGV-3496 | Download Call Recording data and export to csv. | 3 |  | Soumya
|  | UGV-3497 | CR monitoring Setup | 1.5 |  | Hardik
ASC Monitoring Support | UGV-3621 | UGV-3643 | ASC Monitoring Support-1 | 8 |  | Gopal
|  | UGV-3644 | ASC Monitoring Support-2 | 8 |  | Asim
ITSM Validation
ITSM
|  | UGV-3625 | ITSM-75452 ASC Config changes | 1 | Neha | 2021-05-03 02:00
|  | UGV-3626 | ITSM-75460 IDA - Cosmo Patch for 31.65.1906.0 R2011: LDVS.12 | 1 | Neha | 2021-05-06 02:00
|  | UGV-3627 | ITSM-75461 N19 - Cosmo Patch for 31.65.1906.0 R2011: LDVS.12 | 1 | Hardik | 2021-05-06 02:00
|  | UGV-3628 | ITSM-74556 N11 - Cosmo Patch for 31.65.1906.0 R2011: LDVS.12 | 1 | Deevena | 2021-05-06 02:00
|  | UGV-3629 | ITSM-74635 N14 ECC Upgrade | 1 | Neha | 2021-05-07 02:00
|  | UGV-3630 | ITSM-75285 : SID -- Migrate ECC HB from MySQL5.6 to MySQL5.7 CE | 1 | Hardik | 2021-05-07 02:00
|  | UGV-3631 | ITSM-74628 N18 ECC Upgrade | 1 | Neha | 2021-05-11 02:00
|  | UGV-3632 | ITSM-74631 N21 ECC Upgrade | 1 | Hardik | 2021-05-11 02:00
|  | UGV-3633 | ITSM-74633 N23 ECC Upgrade | 1 | Neha | 2021-05-13 02:00
|  | UGV-3634 | ITSM-74630 N20 ECC Upgrade | 1 | Hardik | 2021-05-13 02:00
|  | UGV-3635 | ITSM-74632 N22 ECC Upgrade | 1 | Asim | 2021-05-13 02:00
|  | UGV-3636 | ITSM-74552 WES - Cosmo Patch for 31.65.1906.0 R2011 | 1 | Deevena | 2021-05-13 02:00
|  | UGV-3637 | ITSM-74567 SID - Cosmo Patch for 31.65.1906.0 R2011 | 1 | Hardik | 2021-05-13 22:00
|  | UGV-3638 | ITSM-75422 : N17 ECC Upgrade | 1 | Hardik | 2021-05-14 02:00
|  | UGV-3639 | ITSM-74634 N26 ECC upgrade | 1 | Neha | 2021-05-14 02:00
|  | UGV-3640 | ITSM-74636 AXL ECC upgrade | 1 | Asim | 2021-05-14 02:00
|  | UGV-3641 | ITSM-74559 N16 - Cosmo Patch for 31.65.1906.0 R2011 | 1 | Deevena | 2021-05-14 02:00
|  | UGV-3642 | ITSM-74555 N10 - Cosmo Patch for 31.65.1906.0 R2011 | 1 | Gopal | 2021-05-14 02:00
| KT-Session Soumya | UGV-3574 | Connect Overview | 8 | Soumya
|  | UGV-3575 | Shared Component Overview | 8 | Soumya
| KT Sessions Mohit | UGV-3646 | KT Sessions Mohit | 6 | Mohit
|  | UGV-3665 | ITSM-74975 - Upgrade SBC to build that supports STIR/SHAKEN.(Dallas) | 2.5 | Asim | 5/4/2021 2:00 AM ET
|  | UGV-3666 | ITSM-74975 - Upgrade SBC to build that supports STIR/SHAKEN.(Dallas) | 2.5 | Deevena
|  | UGV-3667 | ITSM-74976 - Upgrade SBC to build that supports STIR/SHAKEN.(Dallas) | 2.5 | Asim | 5/5/2021 2:00 AM ET
|  | UGV-3668 | ITSM-74976 - Upgrade SBC to build that supports STIR/SHAKEN.(Dallas) | 2.5 | Deevena
|  | UGV-3669 | ITSM-75429 - Upgrade SBC to build that supports STIR/SHAKEN.(UK) | 2.5 | Asim | 5/10/2021 9:00 PM ET
|  | UGV-3670 | ITSM-75429 - Upgrade SBC to build that supports STIR/SHAKEN.(UK) | 2.5 | Deevena
|  | UGV-3671 | ITSM-75430 - Upgrade SBC to build that supports STIR/SHAKEN.(UK) | 2.5 | Asim | 5/11/2021 9:00 PM ET
|  | UGV-3672 | ITSM-75430 - Upgrade SBC to build that supports STIR/SHAKEN.(UK) | 2.5 | Deevena
|  | UGV-3663 | ITSM-75465 - Update Incorrect Trunk IP's and Add Geo-Redundancy configuration in AXL | 2 | Asim | 5/12/21 2:00 AM ET
|  | UGV-3664 | ITSM-75466 - Update Incorrect Trunk IP's and Add Geo-Redundancy configuration in IDA | 2 | Deevena | 5/13/21 2:00 AM ET
|  |  | Network ITSM | 5 | Deevena | 2021-05-15
|  |  | Network ITSM | 4 | Asim
Emergency Re-routing |  |  | Emergency Re-routing Architecture | 8 | Gopal
|  |  | Emergency Re-routing Test Plan | 8 | Gopal
| BOSS automation | UGV-1492 | Adding Profiles in BOSS via various methods Primary partition> Assign number in Numbers section | 14 | Sandeep
|  | UGV-1491 | Adding Profiles in BOSS via various methods Primary partition > Profiles tab > Add | 14 | Sandeep
|  | UGV-3687 | Primary Partition validation: Edit Reset pin; Reassign; Unassigned;Import; Export | 14 | Sandeep
|  | UGV-3688 | Create a new tenant, create a new user | 14 | Sandeep
|  | UGV-2902 | enable all the features and test | 21 | Deevena
|  | UGV-3250 | Download Call Recording data and export to csv. | 21 | Hardik
|  | UGV-3689 | Emergency Registration validation (Location) | 14 | Gopal
|  | UGV-3690 | Investigation of email notification TC | 7 | Hardik | Sandeep (Support)
|  | UGV-3691 | Create Elvis user with proper email - reset password and Pin from links received on notifications. | 21 | Hardik | Hardik (Support)
|  | UGV-3692 | Forgot Password - Elvis (Email -Code Based) - Relogin | 14 | Neha
|  | UGV-3693 | Forgot Password - Elvis (Email - Link Based) - Relogin | 14 | Hardik
|  | UGV-3694 | Elvis user without profile login | 21 | Neha
|  | UGV-3695 | Staff User - (Impersonate as DM) - Do add user and login (Elvis) | 14 | Mohit
|  | UGV-3211 | Staff User - (Impersonate as DM) - Do User Password Change and login | 7 | Deevena
|  | UGV-3685 | Staff User - (Impersonate as DM) -Do TN Password Change and login | 7 | Deevena
|  |  | New SBC GCP Isuse Debug and validation | 10 | Gopal
|  |  | New RP for ABC in GCP - validation | 14 | Himanshu

## Sprint1.2 (hidden)
Epic | Story | JiRA ID | Subtask | Effort (hrs.) | Assignee | Remarks
ITSM | UGV-3956 |  | ITSM-75431 - Upgrade SBC to build that supports STIR/SHAKEN.(AUS-MEL) | 5 | Sandeep | 5/19/2021 11:00 AM ET | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
|  |  | ITSM-75432 - Upgrade SBC to build that supports STIR/SHAKEN.(AUS-MEL) | 5 | Sandeep | 5/20/2021 11:00 AM ET | Asim | 10 | 1 | 0.5 | 59.5 | 60.5 | -1 | 7.5h
|  |  | ITSM-75433 - Upgrade SBC to build that supports STIR/SHAKEN(AUS-SYD) | 5 | Deevena | 5/26/2021 11:00 AM ET | Deevena | 10 | 1.5 | 0 | 59.5 | 45 | 14.5
|  |  | ITSM-75434 - Upgrade SBC to build that supports STIR/SHAKEN.(AUS-SYD) | 5 | Deevena | 5/27/2021 11:00 AM ET | Hardik | 10 | 0 | 10 | 0 | 55 | -55
[7 empty] | Himanshu | 10 | 1 | 0 | 44.1 | 52 | -7.9
| UGV-3957 |  | Rollout of 8 additional prod SBCs, remove 4 old prod SBCs from F5 pool | 2 | Asim | 5/17/2021 2:00 AM – | Gopal | 10 | 0 | 0 | 70 | 52.5 | 17.5
|  |  | Rollout of 16 additional prod SBCs, remove 8 old prod SBCs from F5 pool | 2 | Asim | 5/19/2021 2:00 AM – | Neha | 10 | 0 | 9 | 7 | 56 | -49
|  |  | Rollout of 8 additional prod SBCs, remove 16 old prod SBCs from F5 pool | 2 | Asim | 5/21/2021 2:00 AM – | Sandeep | 10 | 1 | 1 | 56 | 62 | -6
|  |  | Removal of any remaining old prod SBCs from F5 pool | 2 | Asim | 5/24/2021 2:00 AM –
[7 empty] | Total | 70 | 4.5 | 20.5 | 296.1 | 383 | -86.9
| UGV-3948 |  | ITSM-75467 - Update Incorrect Trunk IP's and Add Geo-Redundancy configuration in TOM | 2 | Asim |  | StoryPoint | 70 | 4.5 | 20.5 | 42.3 | 54.7143
|  |  | ITSM-75520 Upgrade SREC appliance - N15; N20; N21; N22; N23; N24 | 1 | Neha | 2021-05-18 02:30
|  |  | ITSM-74704 Upgrade N05/08 SMR to v9.6.2102.104 | 1 | Neha | 2021-05-19 02:00
|  |  | ITSM-74706 Upgrade N11/14 SMR to v9.6.2102.104 | 1 | Neha | 2021-05-20 02:00
|  |  | ITSM-74711 Ugrade N23/24 SMR to v9.6.2102.104 | 1 | Hardik | 2021-05-20 02:00
|  |  | ITSM-75505 Upgrade BOSS US PROD to 81.0 version | 1 | Gopal | 2021-05-21 02:00 |  | Planned | Actual | Remarks
|  |  | ITSM-75505 Upgrade BOSS US PROD / CONSOLE(MCSS) to 81.0 version | 1 | Neha | 2021-05-21 02:00 | ITSM | 2 | 6
|  |  | ITSM-74712 Ugrade N26 SMR to v9.6.2102.104 | 1 | Hardik | 2021-05-21 02:00 | Unplanned | 0 | 5 | emg ITSM , Interviews
|  |  | ITSM-74713 Ugrade SKY SMR1/2/3 to v9.6.2102.104 | 1 | Neha | 2021-05-22 02:00 | MCSS | 6 | 0 | EL's
|  |  | ITSM-74705 Upgrade N09/10 SMR to v9.6.2102.104 | 1 | Hardik | 2021-05-23 02:00 | Agile | 2 | 0.5 | Other Task and EL's
|  |  | ITSM-75512 Upgrade BOSS AU PROD to 80.9 version | 1 | Hardik | 2021-05-25 12:00 | CC.Next | 5 | 3 | Other Task and EL's
|  |  | ITSM-75513 Upgrade BOSS UK PROD to 81.0 version | 1 | Neha | 2021-05-25 22:00 | Call2Teams | 3 | 0 | Task was not ready
|  |  | ITSM-75478 Failover testing between Primary Dallas - GCP and the secondary path Chicago | 4 | Hardik | 2021-05-22 02:00 | Sansey ITSM | 3 | 3
|  |  | ITSM-75478 Failover testing between Primary Dallas - GCP and the secondary path Chicago | 4 | Sandeep |  | ASC Support | 2 | 3 | Found issue on code which took time to fix.
[7 empty] | GCP | 8 | 1 | Task was not ready
[7 empty] | BOSS | 6 | 9 | Automate 17 more Elvis TC
UGV-3652 | UGV-3930 |  | SBC Validation | 32 | Asim |  | ASC 2 | 6 | 3 | Approach changed
[7 empty] | SAFE | 13 | 10 | Hardik and Neha did not attended due to EL
2nd ASC Cluster in NA | Test Environment Setup | UGV-3749 | Automation Setup Provisioning on ACE | 2.5 | Hardik |  |  | 56 | 43.5
UGV-3745 | UGV-3746 | UGV-3750 | Perform basic validation on ACE after power on | 3.5 | Asim
| ACE Migration Rollback Support | UGV-3752 | ACE rollback from cluster 1 support | 6 | Himanshu
| UGV-3747 | UGV-3753 | Cleanup of current ASC account and services from ASC cluster 1 | 6 | Himanshu
|  |  | Pre Migration Data collection | 2 | Gopal
|  | UGV-3751 | Pre Migration support for ACE | 5 | Gopal
|  | UGV-3931 | Validation of ACE cluster after cluster fliped to ASC from Telstrat | 4 | Gopal
|  | UGV-3932 | ACE call recording sanity validation after migration | 2 | Sandeep
| CR Setup and Verification on 2nd Cluster | UGV-3754 | ASC Call Recording Validation for new cluster | 6 | Sandeep
| UGV-3748 | UGV-3755 | ASC call Recording Instance Validation | 4 | Gopal
BOSS Automation | UGV-3958 |  | Assign/Edit/Unassign DNIS | 14 | Gopal
|  |  | Staff User - (Impersonate as DM) -Do PIN change | 7 | Hardik
|  | UGV-2902 | Add on Features Activation Automation | 20 | Deevena | Spill from Sprint 1.1
|  |  | BOSS Automation Suite Fixes | 7 | Sandeep
| UGV-3959 |  | Safe Training | 15 | Asim
|  |  | Safe Training | 15 | Deevena
|  |  | Safe Training | 15 | Hardik
|  |  | Safe Training | 15 | Himanshu
|  |  | Safe Training | 15 | Gopal
|  |  | Safe Training | 15 | Sandeep
|  |  | Safe Training | 15 | Neha
| UGV-3960 |  | ASC Call Recording Support | 7.5 | Gopal
|  |  | ASC Call Recording Support | 7.5 | Hardik
| MsTeams Validation for Aus |  |  | 15 | Hardik
| MsTeams KT |  |  | 8 | Himanshu
Continus Learning and Improvement
| UGV-3702 | UGV-3702 | [MCSS Automation] Get Dashboard Content | 7 | Neha
| UGV-2573 | UGV-3703 | [MCSS Automation] Huntgroup Creation | 7 | Neha
|  | UGV-3704 | [MCSS Automation] Huntgroup Fetch | 7 | Neha
|  | UGV-3705 | [MCSS Automation] Huntgroup Update | 7 | Neha
|  | UGV-3706 | [MCSS Automation] Huntgroup delete | 7 | Neha
| UGV-2575 | UGV-3707 | [MCSS Automation] Autoattendent Creation | 7
|  | UGV-3708 | [MCSS Automation] Autoattendent Fetch | 7
|  | UGV-3709 | [MCSS Automation] Autoattendent Update | 7
|  | UGV-3710 | [MCSS Automation] Autoattendent Delete | 7
| CC.Next |  |  | 17 | Himanshu
|  |  |  | 18 | Sandeep

## Sprint1.3 (hidden)
Epic | Story | JiRA ID | Subtask | Effort (hrs.) | Assignee | Remarks | Actuals | Diff | Remarks
[10 empty] | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
| ASC Monitoring Support |  |  | 14 |  |  | 17 | 3 |  | Asim | 10 | 0 | 1 | 63 | 0 | 63
[10 empty] | Deevena | 10 | 0 | 1 | 63 | 0 | 63
| ITSM Validation |  |  | 35 |  |  | 23 | -12 |  | Hardik | 10 | 0 | 7.5 | 17.5 | 0 | 17.5
[10 empty] | Himanshu | 10 | 0 | 2 | 39.2 | 0 | 39.2
| Validation of ASC cluster 2 |  |  | 14 |  |  | 19 | 5 |  | Gopal | 10 | 1 | 2 | 49 | 0 | 49
[10 empty] | Neha | 10 | 0 | 10 | 0 | 0 | 0
| CC.Next |  |  | 28 |  |  | 15 | -13 |  | Sandeep | 10 | 0 | 1 | 63 |  | 63
| SBC Validation |  |  | 35 |  |  | 0 | -35 |  | Total | 70 | 1 | 24.5 | 294.7 | 0 | 294.7
[10 empty] | StoryPoint | 70 | 1 | 24.5 | 42.1 | 0
| ASC Migration 2 Instances |  |  | 180 |  |  | 75 | -105
| DE/FR Prepration |  |  | 28 |  |  | 10 | -18
| MsTeams UK |  |  | 23 |  |  | 0 | -23
| MsTeams AUS |  |  | 23 |  |  | 2 | -21
| RP Validation |  |  | 14 |  |  | 0 | -14
| SBC Validation Automation Fesiblity |  |  | 35 |  |  | 9 | -26
| RayBaum Study and Understanding |  |  | 14 |  |  | 10 | -4
0
| BOSS Automation |  |  | 7 |  |  | 26 | 19 | Staff TC required a fix which took etra time
| UCB Automation Fix |  |  | 8 |  |  | 5 | -3
| Unplanned |  |  | 0 |  |  | 57 | 57

## Sprint1.4 (hidden)
Epic | Story | JiRA ID | Subtask | Effort (hrs.)339 | Assignee | Remarks
[7 empty] | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
| Mitel One CX(CC.Next) Test Plan |  |  | 21 |  |  | Asim | 10 | 2 | 1 | 49 | 0 | 49
[7 empty] | Deevena | 10 | 0 | 1 | 63 | 0 | 63
| Mitel One CX Validation on N24 |  |  | 35 |  |  | Hardik | 10 | 0 | 0 | 70 | 0 | 70
| Mitel One KT |  |  | 10 |  |  | Himanshu | 10 | 1 | 0 | 44.1 | 0 | 44.1
[7 empty] | Gopal | 10 | 1 | 0 | 63 | 0 | 63
| Call2Teams for AUS |  |  | 12 |  |  | Neha | 10 | 0 | 10 | 0 | 0 | 0
| Call2Teams KT |  |  | 7 |  |  | Sandeep | 10 | 0 | 0 | 70 |  | 70
| Call Recording Parllel execution |  |  | 14 |  |  | Total | 70 | 4 | 12 | 359.1 | 0 | 359.1
[7 empty] | StoryPoint | 70 | 4 | 12 | 51.3 | 0
| Call Recording Monitoring Support |  |  | 21
| BOSS UK GCP Migration |  |  | 8
| BOSS AUS GCP Migration |  |  | 8
| DE/FR Testplan |  |  | 21
| CR Migration for N10 |  |  | 28
| ITSM Validation |  |  | 28
| SBC Validation Automation |  |  | 35
| Call Recording Migration Prepration |  |  | 42
| MCSS Automation |  |  | 49
N10 Migration
|  | Automation Setup | Gopal
|  | Monitoring Setup | Gopal
|  | Delta Data Creation | Deevena
| 10:30 | Order Processing | Deevena/Sandeep
| 14:00 | Migration BOSS Validation and Delta data validation | Deevena/Sandeep
|  | Migration PBX Validation1 | Gopal
|  | Migration PBX Validation2 | Sandeep
|  | Automation Execution | Gopal
|  | Billing Correction | Deevena&Gopal
|  | Roles and Groups correction for Delta Data | Asim

## Sprint 1.5 (hidden)
Epic | Story | JiRA ID | Subtask | Effort (hrs.)396 | Assignee | Remarks
[6 empty] | N22 (N22) |  | Mitigation/Backup |  | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort | Planned Leaves Dates
| N22 CR Migration | UGV-3833 | N22 PreConfiguration Checklist | 12 | Gopal | Hardik &Deevena | krishan.gopal@mitel.com |  |  | Asim | 10 | 2 | 0 | 56 | 67.5 | -11.5 | 1st or 2nd July, 5th July
| UGV-3738 | UGV-3834 | N22 AuN22ation Setup PBX and ECC | 8 | Hardik | Hardik | devani.hardik@mitel.com |  |  | Deevena | 10 | 0 | 0 | 70 | 27 | 43
|  | UGV-3835 | N22 CusN22er Account Identification | 3 | Asim | Deevena | asim.jena@mitel.com |  | Deevena | Hardik | 10 | 0 | 0 | 70 | 76 | -6
|  | UGV-3836 | N22 CusN22er Account Data Collection-1 | 8 | Asim | Deevena | asim.jena@mitel.com |  | Gopal | Himanshu | 10 | 1 | 0 | 44.1 | 34 | 10.1 | 2021-06-30
|  | UGV-3837 | N22 CusN22er Account Data Collection-2 |  | Gopal | NA |  |  |  | Gopal | 10 | 0 | 0 | 70 | 33 | 37
|  | UGV-3838 | N22 AuN22ation Setup BOSS | 2 | Himanshu | Himanshu | himanshu.gupta@mitel.com |  |  | Neha | 10 | 0 | 1 | 63 | 15 | 48
|  | UGV-3839 | N22 Price Plan Validation and Trial Orders | 1.5 | Asim | Deevena | asim.jena@mitel.com |  |  | Sandeep | 10 | 0 | 0 | 70 |  | 70
|  | UGV-3840 | N22 PBX Manual Validation | 4 | Hardik | Hardik | devani.hardik@mitel.com
|  | UGV-3841 | N22 Pre Migration ITSM -1 | 6 | Asim | Deevena | asim.jena@mitel.com |  |  | Total | 70 | 3 | 1 | 443.1 | 252.5 | 190.6
|  | UGV-3842 | N22 Pre Migration ITSM -2 |  | Gopal | NA | krishan.gopal@mitel.com |  |  | StoryPoint | 70 | 3 | 1 | 63.3 | 36.0714
|  | UGV-3843 | N22 Pre Migration AuN22ation Tasks | 6 | Himanshu | Himanshu | himanshu.gupta@mitel.com
|  | UGV-3844 | N22 Cutover ITSM BOSS-1 | 4 | Asim | Deevena | asim.jena@mitel.com
|  | UGV-3845 | N22 Pre Cutover ITSM Validation | 2 | Asim | Deevena | krishan.gopal@mitel.com
|  | UGV-3846 | N22 Cutover ITSM PBX-1 | 1.5 | Hardik | Hardik | devani.hardik@mitel.com
|  | UGV-3847 | N22 Cutover ITSM PBX-2 | 1.5 | Deevena | Sandeep | deevena.thota@mitel.com
|  | UGV-3848 | N22 Billing ITSM Validation | 3 | Asim | Deevena | asim.jena@mitel.com
|  | UGV-3849 | N22 AuN22ation Execution | 6 | Himanshu | Himanshu | himanshu.gupta@mitel.com
|  | UGV-3850 | N22 ASC Roles and Group Correction | 3 | Himanshu | Himanshu | himanshu.gupta@mitel.com
|  | UGV-3851 | N22 CR monitoring Setup | 1.5 | Hardik | Hardik | devani.hardik@mitel.com
| TOM CR Migration | UGV-3909 | TOM PreConfiguration Checklist | 12 | Sandeep | Asim & Gopal | Sandeep.Rai@mitel.com
| UGV-3742 | UGV-3910 | TOM AuN22ation Setup PBX and ECC | 8 | Neha | Hardik | neha.kulkarni@mitel.com
|  | UGV-3911 | TOM CusN22er Account Identification | 3 | Deevena | Asim | deevena.thota@mitel.com
|  | UGV-3912 | TOM CusN22er Account Data Collection-1 | 8 | Deevena | Gopal | deevena.thota@mitel.com
|  | UGV-3913 | TOM CusN22er Account Data Collection-2 | 8 | Sandeep | NA | Sandeep.Rai@mitel.com
|  | UGV-3914 | TOM AuN22ation Setup BOSS | 2 | Himanshu | Himanshu | himanshu.gupta@mitel.com
|  | UGV-3915 | TOM Price Plan Validation and Trial Orders | 1.5 | Deevena | Gopal | deevena.thota@mitel.com
|  | UGV-3916 | TOM PBX Manual Validation | 4 | Neha | Asim | neha.kulkarni@mitel.com
|  | UGV-3917 | TOM Pre Migration ITSM -1 | 6 | Deevena | Gopal | deevena.thota@mitel.com
|  | UGV-3918 | TOM Pre Migration ITSM -2 | 6 | Sandeep | NA | Sandeep.Rai@mitel.com
|  | UGV-3919 | TOM Pre Migration AuN22ation Tasks | 6 | Himanshu | Himanshu | himanshu.gupta@mitel.com
|  | UGV-3920 | TOM Cutover ITSM BOSS-1 | 4 | Deevena | Gopal | deevena.thota@mitel.com
|  | UGV-3921 | TOM Cutover ITSM BOSS-2 | 4 | Sandeep | NA | Sandeep.Rai@mitel.com
|  | UGV-3922 | TOM Cutover ITSM PBX-1 | 1.5 | Neha | Hardik | neha.kulkarni@mitel.com
|  | UGV-3923 | TOM Cutover ITSM PBX-2 | 1.5 | Sandeep | Asim | Sandeep.Rai@mitel.com
|  | UGV-3924 | TOM Billing ITSM Validation | 3 | Deevena | Himanshu | deevena.thota@mitel.com
|  | UGV-3925 | TOM AuN22ation Execution | 6 | Himanshu | Himanshu | himanshu.gupta@mitel.com
|  | UGV-3926 | TOM ASC Roles and Group Correction | 3 | Himanshu | Himanshu | himanshu.gupta@mitel.com
|  | UGV-3927 | TOM CR monitoring Setup | 1.5 | Neha | Asim | neha.kulkarni@mitel.com
| UGV-2574 | UGV-3719 | [MCSS AuN22ation] Fetch Call Details | 8 | Asim
|  | UGV-3720 | [MCSS AuN22ation] Fetch CDR Records-Live Answer and TalkTime | 8 | Hardik
| UGV-3698 | UGV-3721 | [MCSS AuN22ation]Fetch Order Details | 12 | Asim
|  | UGV-3722 | [MCSS AuN22ation]Fetch Service Details |  | Asim
| UGV-3699 | UGV-3723 | [MCSS AuN22ation] Fetch Users | 6 | Hardik
|  | UGV-3724 | [MCSS AuN22ation] Select User | 6 | Asim
|  | UGV-3725 | [MCSS AuN22ation] Reset Password for a Profile | 6 | Hardik
|  | UGV-3726 | [MCSS AuN22ation] Close User | 6 | Asim
| UGV-3700 | UGV-3727 | [MCSS AuN22ation] Add service for call recording | 12 | Hardik
|  | UGV-3728 | [MCSS AuN22ation] Delete service for call recording |  | Hardik
|  | UGV-3729 | [MCSS AuN22ation] Add Music File |  | Asim
| UGV-3701 | UGV-3730 | [MCSS AuN22ation] Update Music File to Group |  | Asim
|  | UGV-3731 | [MCSS AuN22ation] Remove Music File |  | Asim
| UGV-3702 | UGV-4212 | [MCSS AuN22ation] Get Dashboard Content 1 | 8 | Hardik
|  | UGV-4213 | [MCSS AuN22ation] Get Dashboard Content 2 | 8 | Asim
|  |  | SBC AuN22ation | 21 | Gopal
|  |  | ECC AuN22ation Improvements | 28
|  |  | KT Session for team | 7
|  |  | CR Migration Prepration | 28
|  |  | CR Monitoring | 21 | Hardik
|  |  | BOSS AuN22ation Fixes | 28 | Sandeep
|  |  | Mitel One CX | 21

## Sprint2.1 (hidden)
Epic | Story | JiRA ID | Subtask | Effort (hrs.)0 | Assignee | Remarks
[7 empty] | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
|  |  | PI2.1 ZED BOSS Validation | 14 | Sandeep |  | Asim | 9 | 0 | 0 | 63 | 78 | -15
|  |  | PI2.1 ZED Automation Execution and PBX Validation | 21 | Asim |  | Deevena | 9 | 1 | 0 | 56 | 47 | 9
[7 empty] | Hardik | 9 | 0 | 0 | 63 | 28 | 35
|  |  | PI2.1 IDA Data Collection | 14 | Gopal |  | Himanshu | 9 | 0 | 0 | 44.1 | 0 | 44.1
|  |  | PI2.1 IDA BOSS Validation | 13 | Gopal |  | Gopal | 9 | 0 | 0 | 63 | 74 | -11
|  |  | PI2.1 IDA and N09 Automation Execution and ASC Role Correction | 18 | Asim |  | Sandeep | 9 | 0 | 0 | 63 | 35 | 28
|  |  | PI2.1 Automation Setup and Manual PBX Validation IDA | 14 | Hardik |  | Mohan | 5 | 0 | 0 | 35 | 14 | 21 | 50% In Validation
|  |  | PI2.1 Automation Setup and Manual PBX Validation N09 | 14 | Mohan |  | Subham | 4 | 0 | 0 | 28 | 14 | 14 | 40% In validation
|  |  | PI2.1 N09 BOSS Validation | 13 | Deevena
|  |  | PI2.1 AXL Data Collection | 21 | Gopal
|  |  | PI2.1 N08 Data Collection | 21 | Sandeep |  | Total | 63 | 1 | 0 | 415.1 | 290 | 125.1
|  |  | PI2.1 URI Data Collection | 21 | Deevena |  | StoryPoint | 63 | 1 | 0 | 59.3 | 41.4286
[7 empty] | 15 |  |  |  | 50.405
|  |  | PI2.1 N08 BOSS Validation | 13 | Gopal
|  |  | PI2.1 N08 Automation Execution and PBX Validation | 21 | Asim
|  |  | PI2.1 URI and AXL Automation Execution and ASC Role Correction | 18 | Asim
|  |  | PI2.1 Automation Setup and Manual PBX Validation URI | 14 | Subham
|  |  | PI2.1 Automation Setup and Manual PBX Validation AXL | 14 | Hardik
|  |  | PI2.1 URI BOSS Validation | 13 | Deevena
|  |  | PI2.1 AXL BOSS Validation | 13 | Gopal
PI2.1 Mitel One and CX

## Sprint 2.2 (hidden)
Epic | Story | JiRA ID | Subtask | Effort (hrs.)89 | Assignee | Remarks
[8 empty] | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
| IDA CR Migration | UGV-3852 | IDA PreConfiguration Checklist | 12 | Sandeep |  | Sandeep.Rai@mitel.com | Asim | 10 | 0 | 0 | 70 | 0 | 70
| UGV-3739 | UGV-3853 | IDA Automation Setup PBX and ECC | 8 | Neha |  | neha.kulkarni@mitel.com | Deevena | 10 | 0 | 0 | 70 | 25.5 | 44.5
|  | UGV-3854 | IDA Customer Account Identification | 3 | Deevena |  | deevena.thota@mitel.com | Hardik | 10 | 0 | 0 | 70 | 0 | 70
|  | UGV-3855 | IDA Customer Account Data Collection-1 | 8 | Deevena |  | deevena.thota@mitel.com | Himanshu | 10 | 0 | 0 | 49 | 17 | 32
|  | UGV-3856 | IDA Customer Account Data Collection-2 | 8 | Sandeep |  | Sandeep.Rai@mitel.com | Gopal | 10 | 0 | 0 | 70 | 0 | 70
|  | UGV-3857 | IDA Automation Setup BOSS | 2 | Himanshu |  | himanshu.gupta@mitel.com | Sandeep | 10 | 0 | 0 | 70 | 31.5 | 38.5
|  | UGV-3858 | IDA Price Plan Validation and Trial Orders | 1.5 | Deevena |  | deevena.thota@mitel.com | Mohan | 0 | 0 | 0 | 0 | 0 | 0 | 50% In Validation
|  | UGV-3859 | IDA PBX Manual Validation | 4 | Neha |  | neha.kulkarni@mitel.com | Subham | 0 | 0 | 0 | 0 | 0 | 0 | 40% In validation
|  | UGV-3860 | IDA Pre Migration ITSM -1 | 6 | Deevena |  | deevena.thota@mitel.com
|  | UGV-3861 | IDA Pre Migration ITSM -2 | 6 | Sandeep |  | Sandeep.Rai@mitel.com
|  | UGV-3862 | IDA Pre Migration Automation Tasks | 6 | Himanshu |  | himanshu.gupta@mitel.com
|  | UGV-3863 | IDA Cutover ITSM BOSS-1 | 4 | Deevena |  | deevena.thota@mitel.com | Total | 60 | 0 | 0 | 399 | 74 | 325
|  | UGV-3864 | IDA Cutover ITSM BOSS-2 | 4 | Sandeep |  | Sandeep.Rai@mitel.com | StoryPoint | 60 | 0 | 0 | 57 | 10.5714
|  | UGV-3865 | IDA Cutover ITSM PBX-1 | 1.5 | Neha |  | neha.kulkarni@mitel.com | 15 |  |  |  | 48.45
|  | UGV-3866 | IDA Cutover ITSM PBX-2 | 1.5 | Sandeep |  | Sandeep.Rai@mitel.com
|  | UGV-3867 | IDA Billing ITSM Validation | 3 | Deevena |  | deevena.thota@mitel.com
|  | UGV-3868 | IDA Automation Execution | 6 | Himanshu |  | himanshu.gupta@mitel.com
|  | UGV-3869 | IDA ASC Roles and Group Correction | 3 | Himanshu |  | himanshu.gupta@mitel.com
|  | UGV-3870 | IDA CR monitoring Setup | 1.5 | Neha |  | neha.kulkarni@mitel.com
N22 Migration

## Sprint 2.3 (hidden)
Epic | Story | JiRA ID | Subtask | Effort (hrs.)52 | Assignee | Remarks
[7 empty] | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
DE | Requirement Analysis BOSS |  |  | 5 |  |  | Asim | 9 | 0 | 0 | 63 | 0 | 63
| DE Validation |  |  | 18 |  |  | Deevena | 9 | 2 | 0 | 49 | 0 | 49 | 11th and 12th
| DECT Setup |  |  | 2 |  |  | Hardik | 9 | 0 | 0 | 63 | 0 | 63
[7 empty] | Himanshu | 9 | 0 | 0 | 44.1 | 0 | 44.1
| Mitel One CX for U01 |  |  | 2 |  |  | Gopal | 9 | 1 | 0 | 56 | 0 | 56
| Mitel One for U01 |  |  | 2 |  |  | Sandeep | 9 | 0 | 0 | 63 | 0 | 63
| Mitel One Mobile Testplan |  |  | 2 |  |  | Mohan | 5 | 0 | 0 | 35 | 0 | 35 | 50% In Validation
[7 empty] | Vinay | 9 | 0 | 0 | 63 | 0 | 63
| ASC monitoring Support |  |  | 2
| Trainings |  |  | 10
|  |  | Jenkins |  |  |  | Total | 68 | 3 | 0 | 436.1 | 0 | 436.1
|  |  | Gitlab- Access |  |  |  | StoryPoint | 68 | 3 | 0 | 62.3 | 0
|  |  | Robot - Framework |  |  |  | 15 |  |  |  | 52.955
Selenium
Python
Jira
| Interviews |  |  | 2
Hakathone
| SBC Automation |  |  | 3
ITSM Validation
| ECC Automation and Demo |  |  | 1
| Connect Client Automation |  |  | 2
| MSTeams Aus |  |  | 1

## Sprint 2.4 (hidden)
Epic | Story | JiRA ID | Subtask | Effort (hrs.)48 | Assignee | Remarks
[7 empty] | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
E01 | BOSS End Testing |  |  | 3 |  |  | Asim | 10 | 1 | 0 | 63 | 0 | 63
| PBX Validation |  |  | 3 |  |  | Deevena | 10 | 0 | 0 | 70 | 0 | 70
|  |  |  | 1 |  |  | Hardik | 10 | 0 | 0 | 70 | 0 | 70
| ASC Call Recording Validation |  |  | 2 |  |  | Himanshu | 10 | 0 | 0 | 49 | 0 | 49
| Connect Client Validation |  |  | 2 |  |  | Gopal | 10 | 0 | 0 | 70 | 0 | 70
| Fax, Scribe and Third Party Test |  |  | 1 |  |  | Sandeep | 10 | 0 | 0 | 70 | 0 | 70
| Global User and Global Number Validation |  |  | 3 |  |  | Mohan | 5 | 0 | 0 | 35 | 0 | 35 | 50% In Validation
| DECT Phones |  |  | 1 |  |  | Vinay | 10 | 0 | 0 | 70 | 0 | 70
10
ITSM | ITSM Validation |  |  | 5
[7 empty] | Total | 75 | 1 | 0 | 497 | 0 | 497
| KT Sessions |  |  | 5 |  |  | StoryPoint | 75 | 1 | 0 | 71 | 0
[7 empty] | 15 |  |  |  | 60.35
| ASC support |  |  | 1
| Mitel One and CX for N23 and N24 |  |  | 5
| MsTeams for UK |  |  | 3
| Hackathone |  |  | 2
| MsTeams For AUS |  |  | 1

## Sprint 2.5 (hidden)
Epic | Story | JiRA ID | Subtask | Effort (hrs.)0 | Assignee | Remarks
[7 empty] | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[7 empty] | Asim | 9 | 0 | 0 | 63 | 0 | 63
[7 empty] | Deevena | 9 | 0 | 0 | 63 | 0 | 63
[7 empty] | Hardik | 9 | 0 | 0 | 63 | 0 | 63
[7 empty] | Himanshu | 9 | 0 | 0 | 44.1 | 0 | 44.1
[7 empty] | Gopal | 9 | 0 | 0 | 63 | 0 | 63
[7 empty] | Sandeep | 9 | 0 | 0 | 63 | 0 | 63
[7 empty] | Mohan | 0 | 0 | 0 | 0 | 0 | 0 | 50% In Validation
[7 empty] | Subham | 0 | 0 | 0 | 0 | 0 | 0 | 40% In validation
[7 empty] | Total | 54 | 0 | 0 | 359.1 | 0 | 359.1
[7 empty] | StoryPoint | 54 | 0 | 0 | 51.3 | 0
[7 empty] | 15 |  |  |  | 43.605

## PI3 Backlogs
E01 | E01 Validation
Msteam validation
Global user validation
MitelONe validation
Mitel CX validation
BOSS validation
Regression
N27 | Instance validation
Raybum | req understanding | Asim
| Test plan | Asim
Msteam | MS team -UK validation
MS team -whilesale UK validation
Global user ms team- UK
Global user ms team- AUS
Global user ms team- US
Automation | SBC automation -80%
Mitel one to mitel one- POC upgrade scope
Ms team POC upgrade scope
Training | PBX validation
Ecc validation
ITSM | PBX ITSM -2105 | this week complete
PBX ITSM -2109
| SBC's to CHI Validation | how many
| SBC's to CHI Cutover | When the cutover planeed
EPIC Partner Managed Key-CPQ
Mitel One and CX deployment

## PI3.1 (hidden)
Epic | Story | JiRA ID | Subtask | Efforts in SP | Spent | Remarks | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[7 empty] | Asim | 10 | 2 | 0 | 56 | 0 | 56
Traning and New Learnings | UCB /Connect Client Training |  |  | 2 | 1 | Some part was already covered in other tainings | Deevena | 10 | 0 | 0 | 70 | 0 | 70
| BOSS |  |  | 2 | 3 | Took extra time than expcted. And completed in multiple sessions | Hardik | 10 | 0 | 0 | 70 | 0 | 70
| 3rd Party |  |  | 1 | 2 | Underplanned effort | Himanshu | 10 | 1 | 0 | 44.1 | 0 | 44.1
| FAX&Scribe |  |  | 1 | 0 | Not Started | Gopal | 10 | 0 | 0 | 70 | 0 | 70
| New Learnings |  |  | 4 | 20 | Utilized the Mitel One CX POD effort in new learning for added areas like framework, ITSM execution process etc. | Sandeep | 10 | 0 | 0 | 70 | 0 | 70
[7 empty] | Mohan | 7.5 | 1 | 0 | 45.5 | 0 | 45.5
ITSM Validation | PBX |  |  | 6 | 1 | No Major ITSM was planned | Vinay | 7.5 | 0 | 0 | 52.5 | 0 | 52.5
| Comnet |  |  | 1 | 0 | No ITSM was planned | Mohit | 5 | 0 | 0 | 35 | 0 | 35
| BOSS |  |  | 2 | 4 | Incident and ITSM shawdoing | Prasanna | 2.5 | 0 | 0 | 17.5 | 0 | 17.5
| Mitel One CX POD ITSM |  |  | 6 | 0 | Not Started | Sourav | 5 | 0 | 0 | 35 | 0 | 35
Improvments | Mitel One Automation |  |  | 3 | 3
[7 empty] | Total | 87.5 | 4 | 0 | 565.6 | 0 | 565.6
E01 | Automation Setup |  |  | 2 | 0 | Not Started | Total Story Points | 87.5 | 4 | 0 | 80.8 | 0
| E01 Debugging Support |  |  | 4 | 7 | Repatative validation for BOSS and ASC due to multiple issues | Buffer (15%) | 12.12
[7 empty] | ITSM(30%) | 24.24 |  | Start Date | 2021-09-20
Mitel one and CX | U01 |  |  | 1 | 1 | Failure Test Pending | Project Support(30%) | 24.24 |  | End Date | 2021-10-01
| U01 CX |  |  | 3 | 2 | Too many Failures with Call | Unplanned(15%) | 12.12
| U01 Mobile |  |  | 2 | 1 | Too many Failures | Learnings (10%) | 8.08
| N23 and N24 Mobile |  |  | 2 | 2 |  | Planned Valocity | 68.68
| N23 and N24 CX Defect Re-test |  |  | 3 | 3
| Mitel One and CX POD 1 |  |  | 3 | 2 | Converted to POD Deployment training as multiple Story having small individual task for Training
| Mitel One and CX POD N15 |  |  | 3 | 3 | Failure Test Pending
| Mitel One and CX POD 3 |  |  | 3 | 0 | Not Ready
| Mitel One and CX POD 4 |  |  | 3 | 0 | Not Ready
Ms Teams | Global User Validation |  |  | 2 | 0 | Not Started
| Defects |  |  | 1 | 3 | Multiple issues during validation
Raybaum | Study |  |  | 3 | 2 | Study part is done.
| Test Plan |  |  | 3 | 1 | TC is also completd and review is pending.
Unplanned Work |  |  |  | 12 | 5 | No major unplanned works
Added Task | Infra ITSM-SBC Validation |  |  | 3 | 7 | SBC phone reg issues, VPN issues from IT and Automation was not ready

## PI3.2 (hidden)
Epic | Story | JiRA ID | Subtask | Efforts in SP | Spent | Remarks | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[7 empty] | Asim | 9 | 2 | 0 | 49 | 0 | 49
Traning and New Learnings | FAX&Scribe |  |  | 1 | 0 | Training Not conducted | Deevena | 9 | 0 | 0 | 63 | 0 | 63
| BOSS training |  |  | 4 | 3 |  | Hardik | 9 | 0 | 0 | 63 | 0 | 63
| Call2Teams |  |  | 2 | 0 | Completed | Himanshu | 9 | 1 | 0 | 39.2 | 0 | 39.2
| New Learnings |  |  | 2 | 7 |  | Gopal | 9 | 1 | 0 | 56 | 0 | 56
ITSM Validation | PBX |  |  | 9 | 4 |  | Sandeep | 9 | 0 | 0 | 63 | 0 | 63
| Mitel One CX POD ITSM |  |  | 3 | 0 |  | Mohan | 6.5 | 1 | 0 | 38.5 | 0 | 38.5
| Infra ITSM |  |  | 2 | 0 |  | Vinay | 9 | 1 | 0 | 56 | 0 | 56
[7 empty] | Mohit | 9 | 0 | 0 | 63 | 0 | 63
[7 empty] | Prasanna | 9 | 0 | 0 | 63 | 0 | 63
Improvments | Mitel One Automation- Call Scenarios Framework |  |  | 4 | 3 |  | Sourav | 9 | 1 | 0 | 56 | 0 | 56
| Mitel One Automation- Pphone python-3.9 |  |  | 2 | 0 | No Effort Logged
| Mitel One Automation- Test Cases |  |  | 2 | 1
[7 empty] | Total | 96.5 | 7 | 0 | 609.7 | 0 | 609.7
[7 empty] | Total Story Points | 96.5 | 7 | 0 | 87.1 | 0
E01 | Automation Setup |  |  | 2 | 1 | Completed for Global User Only | Buffer (15%) | 13.065
| E01 Debugging Support |  |  | 4 | 4 |  | ITSM(30%) | 26.13 |  | Start Date | 2021-10-04
| E01 Global User |  |  | 2 | 2 |  | Project Support(30%) | 26.13 |  | End Date | 2021-10-15
| E01 Global Number and TollFree |  |  | 2 | 2 |  | Unplanned(15%) | 13.065
| E01 Mitel One Validation |  |  | 2 |  | Not working | Learnings (10%) | 8.71
| E01 CX Validation |  |  | 3 |  | Not working | Planned Valocity | 74.035
| E01 BOSS Issue Re-validation |  |  | 2 | 2
| BOSS Cutover Validation AU |  |  | 2 | 0 | Not Came
| BOSS Cutover Validation UK |  |  | 2 | 0 | Not Came
Unplanned Work |  |  |  | 12 | 6
| Mitel One and CX Unplanned |  |  | 0 | 6 | Seprated the Unplanned for mitel one and CX to Mitel CX epic
Mitel one and CX | U01 CX and Mitel one. |  |  | 3 | 1 | Issue
| Mobile App Validation U01 |  |  | 1 | 1
| N23 and N24 CX Defect Re-test |  |  | 3 | 3
| Mitel One and CX N18 Validation |  |  | 2 | 2
| Mitel One and CX N15 Validation |  |  | 2 | 1 | Only Sanity Done
| Mitel One and CX ZED Validation |  |  | 3 | 4
| Mitel One and CX Sanity Validation |  |  | 3 | 4
CR monitoring | CR monitoring Deevena & Vinay |  |  | 1 | 1

## PI3.3 (hidden)
Epic | Story | JiRA ID | Subtask | Efforts in SP | Spent | Remarks | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[7 empty] | Asim | 10 | 2 | 0 | 56 | 0 | 56
Traning and New Learnings | FAX&Scribe |  |  | 1 | 0 |  | Deevena | 10 | 0 | 0 | 0 | 0 | 0
| New Learnings |  |  | 2 | 1 |  | Hardik | 10 | 0 | 0 | 70 | 0 | 70
[7 empty] | Himanshu | 10 | 1 | 0 | 44.1 | 0 | 44.1
[7 empty] | Gopal | 10 | 0 | 0 | 70 | 0 | 70
[7 empty] | Sandeep | 10 | 0 | 0 | 70 | 0 | 70
ITSM Validation | PBX-2109 |  |  | 8 | 5 | Many got cancled | Mohan | 7.5 | 1 | 0 | 45.5 | 0 | 45.5
| PBX |  |  | 4 | 7 |  | Vinay | 10 | 1 | 0 | 63 | 0 | 63
| Infra ITSM |  |  | 2 | 0 | No ITSM | Mohit | 10 | 0 | 0 | 70 | 0 | 70
[7 empty] | Prasanna | 10 | 0 | 0 | 70 | 0 | 70
Improvments | Mitel One Automation- PBX Call Scenarios Framework |  |  | 4 | 3 |  | Sourav | 10 | 0 | 0 | 70 | 0 | 70
| Mitel One Automation- Test Cases |  |  | 4 | 3
| N14 HB4 Setup |  |  | 1 | 1
[7 empty] | Total | 107.5 | 5 | 0 | 628.6 | 0 | 628.6
[7 empty] | Total Story Points | 107.5 | 5 | 0 | 89.8 | 0
E01 | Automation Setup |  |  | 2 | 2 |  | Buffer (15%) | 13.47
| E01 Debugging Support |  |  | 4 | 4 |  | ITSM(30%) | 26.94 |  | Start Date | 2021-10-18
| E01 Global User |  |  | 1 | 2 | AUS call was failing -- Issue debugging | Project Support(30%) | 26.94 |  | End Date | 2021-10-29
| E01 Global Number and TollFree |  |  | 1 | 1 |  | Unplanned(15%) | 13.47
| E01 Mitel One Validation |  |  | 2 | 0 | Not Started | Learnings (10%) | 8.98
| E01 CX Validation |  |  | 3 | 0 | Not Started | Planned Valocity | 76.33
| E01 BOSS Issue Re-validation |  |  | 2 | 1
| E01 ABC and RP validation |  |  | 1 | 0 | Not Started
Unplanned Work |  |  |  | 12 | 8
Mitel one and CX | U01 CX and Mitel one. |  |  | 2 | 1 | Some Issue fixes is still pending
| Mitel One and CX N18 Validation |  |  | 3 | 3
| Mitel One and CX Debugging support |  |  | 4 | 6
| Mitel One and CX N15 Validation |  |  | 2 | 2
| Mitel One and CX ZED Validation |  |  | 2 | 2
| Mitel One Sanity Validation |  |  | 2 | 2
| Mitel N14 CX Validation |  |  | 3 | 3
| Mitel One and CX Defects Validation |  |  | 1 | 1
| Mitel One and CX N16 Validation |  |  | 3 | 1 | Mitel One Done
CR monitoring | CR monitoring Gopal & Mohan |  |  | 1 | 1
Mitel One Monitoring | Mitel One Monitoring |  |  | 2 | 2
| N20 |  |  |  | 3
| N26 |  |  |  | 3
| N19 |  |  |  | 2
| N22 |  |  |  | 2
| WES |  |  |  | 1
| URI |  |  |  | 3
| N05 |  |  |  | 1

## PI3.4 (hidden)
Epic | Story | JiRA ID | Subtask | Efforts in SP | Spent | Remarks | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[7 empty] | Asim | 8 | 2 | 0 | 42 | 0 | 42
ITSM Validation | PBX-2109 |  |  | 8 | 11 |  | Hardik | 8 | 2 | 0 | 42 | 0 | 42
| PBX |  |  | 4 | 3 |  | Himanshu | 8 | 2 | 0 | 29.4 | 0 | 29.4
| Infra ITSM |  |  | 2 | 1 |  | Gopal | 8 | 4 | 0 | 28 | 0 | 28
Traning and New Learnings | Trainings |  |  | 2 | 4 |  | Sandeep | 8 | 0 | 0 | 56 | 0 | 56
CR monitoring | CR monitoring Himanshu & Sourabh |  |  | 1 | 1 |  | Mohan | 6 | 2 | 0 | 28 | 0 | 28
| Unplanned |  |  | 12 | 7 |  | Vinay | 8 | 0 | 0 | 56 | 0 | 56
[7 empty] | Mohit | 8 | 0 | 0 | 56 | 0 | 56
Raybaum | Raybaum |  |  | 3 | 6 |  | Prasanna | 8 | 0 | 0 | 56 | 0 | 56
| ERS | [5 empty] | Sourav | 8 | 0 | 0 | 56 | 0 | 56
| E01Mitel One |  |  | 2 | 0 |  | Total | 78 | 12 | 0 | 449.4 | 0 | 449.4
| E01 CX |  |  | 3 | 0 |  | Total Story Points | 78 | 12 | 0 | 64.2 | 0
E01 | E01 BOSS Issue Re-validation |  |  | 1 | 1 |  | Buffer (15%) | 9.63
| E01 BOSS Issue Re-validation |  |  | 4 | 1 |  | ITSM(30%) | 19.26 |  | Start Date | 2021-11-01
[7 empty] | Project Support(30%) | 19.26 |  | End Date | 2021-11-12
Mitel one and CX | Mitel One and CX WES Validation |  |  | 2 | 2 |  | Unplanned(15%) | 9.63
| Mitel One and CX N05 Validation |  |  | 2 | 2 |  | Learnings (10%) | 6.42
| Mitel One and CX Debugging support |  |  | 4 | 0 |  | Planned Valocity | 54.57
| Mitel One Defect Validation |  |  | 2 | 1
| Mitel CX Defect Validation |  |  | 3 | 2
| Mitel One and CX TOM Validation |  |  | 3 | 1
| Mitel One and CX N08 Validation |  |  | 3 | 2
Mitel One Monitoring | Mitel One Monitoring |  |  | 1 | 1
Automation | Mitel One Messages |  |  | 4 | 0
| Mitel One Phone |  |  | 2 | 0
Improvments | Mitel One Automation- Capture Fauilure Logs
Mitel One Automation- Messaging
Mitel One Automation- pPhone

## PI3.5 (hidden)
Epic | Story | JiRA ID | Subtask | Efforts in SP | Spent | Remarks | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[7 empty] | Asim | 10 | 2 | 0 | 56 | 0 | 56
Raybaum | GCP and GCVE POD Validation -ITSM2 D2 Changes |  |  | 5 | 2 |  | Hardik | 10 | 1 | 0 | 63 | 0 | 63
| RayBaum Full Validation -ITSM3 | [5 empty] | Himanshu | 10 | 1 | 0 | 44.1 | 0 | 44.1
| Test Emergency Service for All PODS 911/933 After ITSM3 | [5 empty] | Gopal | 10 |  | 0 | 70 | 0 | 70
| Raybaum Planning and Doc |  |  | 5 | 14 |  | Sandeep | 10 | 7 | 0 | 21 | 0 | 21
ERS |  |  |  | 4 | 2 |  | Mohan | 7 | 1 | 0 | 42 | 0 | 42
[7 empty] | Vinay | 10 |  | 0 | 70 | 0 | 70
[7 empty] | Mohit | 10 | 1 | 0 | 63 | 0 | 63
ITSM | PBX-2109 |  |  | 8 | 9 |  | Prasanna | 10 | 0 | 0 | 70 | 0 | 70
| PBX |  |  | 4 | 4 |  | Sourav | 10 | 1 | 0 | 63 | 0 | 63
| PBX2109-AU POD's |  |  | 2 |  | Mohit and Mohan-A02-19-Nov Sourav and Vinay-VAL-20-Nov
[7 empty] | Total | 97 | 14 | 0 | 562.1 | 0 | 562.1
Automation | Connect Client Automation |  |  | 5 | 5 |  | Total Story Points | 97 | 14 | 0 | 80.3 | 0
| Polycom Automation |  |  | 4 | 2 |  | Buffer (15%) | 12.045
| 69xx Automation | [5 empty] | ITSM(30%) | 24.09 |  | Start Date | 2021-11-15
| cross functional end-point automation | [5 empty] | Project Support(30%) | 24.09 |  | End Date | 2021-11-26
| Faster Execution | [5 empty] | Unplanned(15%) | 12.045
[7 empty] | Learnings (10%) | 8.03
Unplanned Task |  |  |  | 12 | 5 | Vinay-OnCall | Planned Valocity | 68.255
| CR mon |  |  | 1 | 2

## PI3.6 (hidden)
Epic | Story | JiRA ID | Subtask | Efforts in SP | Spent | Remarks | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[7 empty] | Asim | 10 | 1 | 0 | 63 | 0 | 63
Raybaum | GCP and GCVE POD Validation -ITSM2 D2 Changes |  |  | 5 |  |  | Hardik | 10 | 1 | 0 | 63 | 0 | 63
| RayBaum Full Validation -ITSM3 |  |  | 5 |  |  | Himanshu | 10 |  | 0 | 49 | 0 | 49
| Test Emergency Service for All PODS 911/933 After ITSM3 |  |  | 2 |  |  | Gopal | 10 |  | 0 | 70 | 0 | 70
| PI3.6 Raybaum Planning and Doc |  |  | 2 |  |  | Sandeep | 10 | 8 | 0 | 14 | 0 | 14
| PI3.6 Raybaum KT and Learnings |  |  | 5 |  |  | Mohan | 7 | 4 | 0 | 21 | 0 | 21
[7 empty] | Vinay | 10 |  | 0 | 70 | 0 | 70
ERS | PI3.6 ERS Handson and Test Planning |  |  | 5 |  |  | Mohit | 10 | 0.5 | 0 | 66.5 | 0 | 66.5
[7 empty] | Prasanna | 10 | 8 | 0 | 14 | 0 | 14
ITSM | PI3.6 PBX-2109 AUS and UK |  |  | 2 |  |  | Sourav | 10 |  | 0 | 70 | 0 | 70
| PI3.6 PBX |  |  | 4
| PI3.6 BOSS Upgrade |  |  | 1
[7 empty] | Total | 97 | 22.5 | 0 | 500.5 | 0 | 500.5
Automation | PI3.6 Connect Client Automation Upgrade suite |  |  | 5 |  |  | Total Story Points | 97 | 22.5 | 0 | 71.5 | 0
| PI3.6 Connect Client Automation UCB suite |  |  | 5 |  |  | Buffer (15%) | 10.725
[7 empty] | ITSM(30%) | 21.45 |  | Start Date | 2021-11-15
[7 empty] | Project Support(30%) | 21.45 |  | End Date | 2021-11-26
Unplanned Task | PI3.6 Unplanned Task |  |  | 12 |  |  | Unplanned(15%) | 10.725
[7 empty] | Learnings (10%) | 7.15
| PI3.6 CR monitoring [Mohit, Vinay] |  |  | 1 |  |  | Planned Valocity | 60.775
| PI3.6 Knowledge Sharing Sessions |  |  | 5
Polycom Automation
69xx Automation
cross functional end-point automation
Faster Execution

## PI3.7 (hidden)
Epic | Story | JiRA ID | Subtask | Efforts in SP | Spent | Remarks | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[7 empty] | Asim | 9 | 4 | 0 | 35 | 0 | 35 | 1 Compoff
Raybaum | Training for COPS team -Raybaum |  |  | 1 |  |  | Hardik | 9 | 0 | 0 | 63 | 0 | 63 | 1 Compoff
| RayBaum Full Validation -ITSM3 |  |  | 10 |  |  | Himanshu | 9 |  | 0 | 44.1 | 0 | 44.1 | 1 Compoff
| Test Emergency Service for All PODS 911/933 After ITSM3 |  |  | 2 |  |  | Gopal | 9 | 1 | 0 | 56 | 0 | 56 | 1 Compoff
| Mitel One Ray baum validation for N23/N24 |  |  | 1 |  |  | Sandeep | 9 |  | 0 | 63 | 0 | 63 | 1 Compoff
| Raybaum regression and defect support |  |  | 10 |  |  | Mohan | 6 |  | 0 | 42 | 0 | 42 | 1 Compoff
[7 empty] | Vinay | 9 |  | 0 | 63 | 0 | 63 | 1 Compoff
ITSM | PI3.6 PBX-2109 AUS and UK |  |  | 2 |  |  | Mohit | 9 |  | 0 | 63 | 0 | 63 | 1 Compoff
| PI3.6 PBX |  |  | 5 |  |  | Prasanna | 10 |  | 0 | 70 | 0 | 70
[7 empty] | Sourav | 9 |  | 0 | 63 | 0 | 63 | 1 Compoff
Unplanned Task | PI3.6 Unplanned Task |  |  | 12
| PI3.6 Knowledge Sharing Sessions |  |  | 10 |  |  | Total | 88 | 5 | 0 | 562.1 | 0 | 562.1
[7 empty] | Total Story Points | 88 | 5 | 0 | 80.3 | 0
| PI3.6 CR monitoring [Mohit, Vinay] |  |  | 1 |  |  | Buffer (15%) | 12.045
[7 empty] | ITSM(30%) | 24.09 |  | Start Date | 2021-12-13
| Bitbucket |  |  | 2 |  |  | Project Support(30%) | 24.09 |  | End Date | 2021-12-24
[7 empty] | Unplanned(15%) | 12.045
| Monitoring Suite Setup |  |  | 5 |  |  | Learnings (10%) | 8.03
[7 empty] | Planned Valocity | 68.255
| End point automation |  |  | 5
| Documentation for Execution |  |  | 5

## PI3.8
Epic | Story | JiRA ID | Subtask | Efforts in SP | Spent | Remarks | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[7 empty] | Asim | 9 |  | 0 | 63 | 0 | 63
Raybaum | Raybaum Simulator Training |  |  | 1 |  |  | Hardik | 9 |  | 0 | 63 | 0 | 63
| Raybaum Defect Support |  |  | 3 |  |  | Himanshu | 9 | 1 | 0 | 39.2 | 0 | 39.2 | 2022-01-05 | --Mohit, Vinay (T1),
[7 empty] | Gopal | 9 |  | 0 | 63 | 0 | 63 |  | --Gopal, Mohan (T2),
Automation | Bit-Bucket migration |  |  | 3 |  |  | Sandeep | 9 |  | 0 | 63 | 0 | 63 |  | --Himanshu, Sourav (T3),
| Phone Audio capturing with Phone Team |  |  | 3 |  |  | Mohan | 6 |  | 0 | 42 | 0 | 42 |  | --Hardik, Asim (T4),
| Monitoring for Connect |  |  | 4 |  |  | Vinay | 9 |  | 0 | 63 | 0 | 63 |  | Sandeep, Prasanna(T5)
| Automation Documentation |  |  | 4 |  |  | Mohit | 9 |  | 0 | 63 | 0 | 63
| CSV Optimization |  |  | 4 |  |  | Prasanna | 9 |  | 0 | 63 | 0 | 63
| Jenkins and Framework Documentation | 5129 |  | 4 |  |  | Sourav | 9 |  | 0 | 63 | 0 | 63
| PBX Upgrade Suite enhancements |  |  | 3 |  |  | Jyoti | 3 |  | 0 | 21 | 0 | 21
| Connect client and Pphone Audio Validation |  |  | 5
[7 empty] | Total | 90 | 1 | 0 | 606.2 | 0 | 606.2
| SBC |  |  | 3 |  |  | Total Story Points | 90 | 1 | 0 | 86.6 | 0
| Fax&Scribe |  |  | 1 |  |  | Buffer (15%) | 12.99
| ABC |  |  | 3 |  |  | ITSM(30%) | 25.98 |  | Start Date | 2022-01-03
[7 empty] | Project Support(30%) | 25.98 |  | End Date | 2021-01-14
Unplanned Task | PI3.6 Unplanned Task |  |  | 12 |  |  | Unplanned(15%) | 12.99
[7 empty] | Learnings (10%) | 8.66
CR Monitoring | PI3.6 CR monitoring [Himanshu,Sourav] |  |  | 1 |  |  | Planned Valocity | 73.61
ITSM | PI3.6 PBX |  |  | 7
| PI3.8 BOSS Upgrade |  |  | 3
| Silk Central Demo |  |  | 2
CR-Data Migration | Check Automation Fesiblity |  |  | 3

## PI3.9
Epic | Story | JiRA ID | Subtask | Efforts in SP | Spent | Remarks | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[7 empty] | Asim | 9 |  | 0.5 | 59.5 | 0 | 59.5
Raybaum | Raybaum Defect Support |  |  | 4 |  |  | Hardik | 9 |  | 0 | 63 | 0 | 63
[7 empty] | Himanshu | 9 |  | 0 | 44.1 | 0 | 44.1 | --Mohit, Vinay (T1),
[7 empty] | Gopal | 9 |  | 1.5 | 52.5 | 0 | 52.5 | --Gopal, Mohan (T2),
Automation | Raybaum validation with address api |  |  | 3 |  |  | Sandeep | 9 |  | 2 | 49 | 0 | 49 | --Himanshu, Sourav (T3),
| Raybaum automation improvement and fix |  |  | 2 |  |  | Mohan | 6 |  | 0 | 42 | 0 | 42 | --Hardik, Asim (T4),
| CSV Optimization Demo prepration with DB |  |  | 3 |  |  | Vinay | 9 |  | 0 | 63 | 0 | 63 | Sandeep, Prasanna(T5)
[7 empty] | Mohit | 9 |  | 4 | 35 | 0 | 35
| Call Recording Data migration 2 pods |  |  | 3 |  |  | Prasanna | 9 |  | 8 | 7 | 0 | 7
| Call Recording Data migration 2 pods |  |  | 3 |  |  | Sourav | 9 |  | 0 | 63 | 0 | 63
[7 empty] | Jyoti | 3 |  | 0 | 21 | 0 | 21
| TURN Server Validation |  |  | 3
| RP Validation |  |  | 3 |  |  | Total | 90 | 0 | 16 | 499.1 | 0 | 499.1
| ABC Validation |  |  | 2 |  |  | Total Story Points | 90 | 0 | 16 | 71.3 | 0
[7 empty] | Buffer (15%) | 10.695
| ITSM Validation |  |  | 10 |  |  | ITSM(30%) | 21.39 |  | Start Date | 2022-01-17
[7 empty] | Project Support(30%) | 21.39 |  | End Date | 2021-01-28
Unplanned Task | PI3.6 Unplanned Task |  |  | 12 |  |  | Unplanned(15%) | 10.695
[7 empty] | Learnings (10%) | 7.13
CR Monitoring | PI3.6 CR monitoring [Hardik,Asim] |  |  | 1 |  |  | Planned Valocity | 60.605
933 Monitoring | Raybaum monitoring Setup |  |  | 2
| NOC team Automation Setup |  |  | 5

## PI3.10
Epic | Story | JiRA ID | Subtask | Efforts in SP | Spent | Remarks | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[7 empty] | Asim | 10 | 1 | 0 | 63 | 0 | 63
[7 empty] | Hardik | 10 | 1 | 0 | 63 | 0 | 63
[7 empty] | Himanshu | 10 |  | 0 | 49 | 0 | 49
Unplanned Task | PI3.6 Unplanned Task |  |  | 12 |  |  | Gopal | 10 |  | 0 | 70 | 0 | 70
[7 empty] | Sandeep | 10 |  | 0 | 70 | 0 | 70
CR Monitoring | PI3.6 CR monitoring [Gopal, Mohan] |  |  | 1 |  |  | Mohan | 10 | 1 | 0 | 63 | 0 | 63
[7 empty] | Vinay | 10 | 1 | 0 | 63 | 0 | 63
ITSM Validation | ITSM Validation |  |  | 10 |  |  | Prasanna | 10 |  | 0 | 70 | 0 | 70
[7 empty] | Sourav | 10 |  | 0 | 70 | 0 | 70
| CR Migration |  |  | 4 |  |  | Jyoti | 3 |  | 0 | 21 | 0 | 21
[7 empty] | Total | 93 | 4 | 0 | 602 | 0 | 602
Automation | Python 3.9 Framework Testing |  |  | 2 |  |  | Total Story Points | 93 | 4 | 0 | 86 | 0
| Polycom Automation Registration |  |  | 5 |  |  | Buffer (15%) | 12.9
| Dashboard setup for Monitoring |  |  | 3 |  |  | ITSM(30%) | 25.8 |  | Start Date | 2022-01-31
| CSV Optimization |  |  | 4 |  |  | Project Support(30%) | 25.8 |  | End Date | 2021-02-11
| OCOM API for Voice Validation |  |  | 5 |  |  | Unplanned(15%) | 12.9
| Trunk Switch Valdaiton |  |  | 5 |  |  | Learnings (10%) | 8.6
| NewRelic and Jenkins Intigration |  |  | 5 |  |  | Planned Valocity | 73.1
| RTP and TURN Server validation |  |  | 7
| ABC Automation Intigration |  |  | 8
| Raybaum configuration Automation |  |  | 7

## PI3.11
Epic | Story | JiRA ID | Subtask | Efforts in SP | Spent | Remarks | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[7 empty] | Asim | 10 | 1 | 0 | 63 | 0 | 63
[7 empty] | Hardik | 10 | 3 | 0 | 49 | 0 | 49
[7 empty] | Himanshu | 10 | 2 | 0 | 39.2 | 0 | 39.2
Unplanned Task | PI3.6 Unplanned Task |  |  | 12 |  |  | Gopal | 10 |  | 0 | 70 | 0 | 70
[7 empty] | Sandeep | 10 |  | 0 | 70 | 0 | 70
CR Monitoring | PI3.6 CR monitoring [Sandeep, Vinay] |  |  | 1 |  |  | Mohan | 10 |  | 0 | 70 | 0 | 70
[7 empty] | Vinay | 10 |  | 0 | 70 | 0 | 70
ITSM Validation | ITSM Validation |  |  | 10 |  |  | Prasanna | 10 |  | 0 | 70 | 0 | 70
[7 empty] | Sourav | 10 | 1 | 0 | 63 | 0 | 63
Automation | Phone Switch validation |  |  | 5 |  |  | Jyoti | 3 |  | 0 | 21 | 0 | 21
| Python 3.9 Framework Testing |  |  | 2
| Polycom Automation Registration |  |  | 5 |  |  | Total | 93 | 7 | 0 | 585.2 | 0 | 585.2
| Dashboard setup for Monitoring |  |  | 3 |  |  | Total Story Points | 93 | 7 | 0 | 83.6 | 0
| Raybaum Address validation with Iq |  |  | 2 |  |  | Buffer (15%) | 12.54
| Sky Phone Automation |  |  | 2 |  |  | ITSM(30%) | 25.08 |  | Start Date | 2022-02-14
| CSV Optimization |  |  | 4 |  |  | Project Support(30%) | 25.08 |  | End Date | 2021-02-25
| OCOM API for Voice Validation |  |  | 5 |  |  | Unplanned(15%) | 12.54
| Trunk Switch Valdaiton |  |  | 5 |  |  | Learnings (10%) | 8.36
| Call Recording Automation Fix |  |  | 1 |  |  | Planned Valocity | 71.06
| NewRelic and Jenkins Intigration |  |  | 5

## PI22.1.1
Epic | Story | JiRA ID | Subtask | Efforts in SP | Spent | Remarks | Owner | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[8 empty] | Asim | 6 | 2 | 0 | 28 | 0 | 28
[8 empty] | Hardik | 6 |  | 0 | 42 | 0 | 42
[8 empty] | Himanshu | 6 | 2 | 0 | 19.6 | 0 | 19.6
Unplanned Task | PI3.6 Unplanned Task |  |  | 6 |  |  |  | Gopal | 6 |  | 0 | 42 | 0 | 42
[8 empty] | Sandeep | 6 |  | 0 | 42 | 0 | 42
CR Monitoring | PI3.6 CR monitoring [Sandeep, Vinay] |  |  | 1 |  |  |  | Mohan | 6 |  | 0 | 42 | 0 | 42
[8 empty] | Vinay | 6 |  | 0 | 42 | 0 | 42
ITSM Validation | ITSM Validation |  |  | 6 |  |  |  | Prasanna | 6 |  | 0 | 42 | 0 | 42
[8 empty] | Sourav | 6 | 1 | 0 | 35 | 0 | 35
Automation | Phone Switch validation |  |  | 5 |  | Done |  | Jyoti | 3 |  | 0 | 21 | 0 | 21
| Python 3.9 Framework Testing |  |  | 2 |  | In Progress | Gopal / Prasanna
| Polycom Automation Registration |  |  | 5 |  | In Progress | Gopal | Total | 57 | 5 | 0 | 355.6 | 0 | 355.6
| Dashboard setup for Monitoring |  |  | 3 |  |  | Prasanna / Hardik | Total Story Points | 57 | 5 | 0 | 50.8 | 0
| Raybaum Address validation with Iq |  |  | 2 |  |  | Sandeep | Buffer (15%) | 7.62
| Sky Phone Automation |  |  | 2 |  |  |  | ITSM(30%) | 15.24 |  | Start Date | 2022-03-03
| CSV Optimization |  |  | 2 |  | In Progress | Prasanna / Hardik | Project Support(30%) | 15.24 |  | End Date | 2022-03-16
| OCOM API for Voice Validation |  |  | 5 |  |  | Himanshu / Sourav | Unplanned(15%) | 7.62
| Trunk Switch Valdaiton |  |  | 5 |  |  | Asim / Mohan | Learnings (10%) | 5.08
| Call Recording Automation Fix |  |  | 1 |  |  | Gopal | Planned Valocity | 43.18
| NewRelic and Jenkins Intigration |  |  | 5 |  |  | Prasanna / Hardik
| RTP Engine & Turn Server Automation |  |  | 7 |  | In Progress | Sandeep
| Raybaum configuration automation |  |  | 7 |  |  | Sandeep / Vinay
ECC Decomision | ECC decomission Discussions & Test plan preparation |  |  | 4
IM Server Decomission | IM server decomission discussions & test plan preparation |  |  | 2
Auditing for the NewRelic monitoring | Initial discussions and documentation |  |  | 1
KT Sessions |  |  |  | 2

## PI22.1.2
Epic | Story | JiRA ID | Subtask | Efforts in SP | Spent | Remarks | Owner | account_id | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[9 empty] | Asim | 9 | 1 | 0 | 56 | 0 | 56
[9 empty] | Hardik | 9 |  | 0 | 63 | 0 | 63
[9 empty] | Prasanna | 9 | 1 | 0 | 39.2 | 0 | 39.2
Unplanned Task | PI3.6 Unplanned Task |  |  | 11 |  |  |  |  | Gopal | 9 | 1 | 0 | 56 | 0 | 56
[9 empty] | Sandeep | 9 | 1 | 0 | 56 | 0 | 56
CR Monitoring | PI3.6 CR monitoring [Sandeep, Vinay] |  |  | 1 |  |  |  |  | Mohan | 9 | 1 | 0 | 56 | 0 | 56
[9 empty] | Vinay | 9 |  | 0 | 63 | 0 | 63
ITSM Validation | ITSM Validation |  |  | 10 |  |  |  |  | Himanshu | 9 |  | 0 | 63 | 0 | 63
[9 empty] | Sourav | 9 | 1 | 0 | 56 | 0 | 56
| Validation - N17 Call recording data migration to ASC | [7 empty] | Jyoti | 3 | 1 | 0 | 14 | 0 | 14
| Validation - N18 Call recording data migration to ASC |  |  | 1
| Client - Support MiCloud Connect SMS to 988 Feature validation |  |  | 2 |  |  |  |  | Total | 84 | 6 | 0 | 522.2 | 0 | 522.2
KT Sessions | KT and Learning Sessions |  |  | 5 |  |  |  |  | Total Story Points | 84 | 6 | 0 | 74.6 | 0
Auditing for the NewRelic monitoring | Initial discussions and documentation |  |  | 1 |  |  |  |  | Buffer (15%) | 11.19
ECC Decomision | ECC decomission Discussions & Test plan preparation |  |  | 4 |  |  |  |  | ITSM(30%) | 22.38 |  | Start Date | 2022-03-17
IM Server Decomission | IM server decomission discussions & test plan preparation |  |  | 2 |  |  |  |  | Project Support(30%) | 22.38 |  | End Date | 2022-03-30
| Automation documentation |  |  | 5 |  |  |  |  | Unplanned(15%) | 11.19
Automation | Python 3.9 Framework Testing |  |  | 5 |  | In Progress | Gopal / Prasanna |  | Learnings (10%) | 7.46
| Polycom Automation Registration |  |  | 3 |  | In Progress | Gopal |  | Planned Valocity | 63.41
| RTP Engine & Turn Server Automation |  |  | 7 |  | In Progress | Sandeep
| NewRelic and Jenkins Intigration |  |  | 5 |  |  | Prasanna / Hardik
| Raybaum configuration automation |  |  | 7 |  |  | Sandeep / Vinay
| Phone Switch validation |  |  | 5 |  | Done
| Dashboard setup for Monitoring |  |  | 3 |  |  | Prasanna / Hardik
| Raybaum Address validation with Iq |  |  | 2 |  |  | Sandeep
| Sky Phone Automation |  |  | 2
| CSV Optimization |  |  | 2 |  | In Progress | Prasanna / Hardik
| OCOM API for Voice Validation |  |  | 5 |  |  | Himanshu / Sourav
| Trunk Switch Valdaiton |  |  | 5 |  |  | Asim / Mohan
| Call Recording Automation Fix |  |  | 1 |  |  | Gopal
1
2
| Encrypt Password in CallRecordingCluster table Jira #: SBOSS-37030 |  |  | 1
| Encrypt Password in device_router table Jira #: SBOSS-37032 |  |  | 1
| Encrypt Password in ShoretelMobilityProfile table Jira #: SBOSS-37039 |  |  | 1
| Encrypt Password in ECCCluster table Jira #: SBOSS-37033 |  |  | 1

## PI22.1.3
Epic | Story | JiRA ID | Subtask | Efforts in SP | Spent | Remarks | Owner | account_id | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[9 empty] | Asim | 10 | 2 | 0 | 56 | 0 | 56
[9 empty] | Hardik | 10 |  | 0 | 70 | 0 | 70
[9 empty] | Prasanna | 10 |  | 0 | 49 | 0 | 49
Unplanned Task | PI22.1.3 Unplanned Task |  |  | 12 |  |  |  |  | Gopal | 10 | 0.5 | 0 | 66.5 | 0 | 66.5
[9 empty] | Sandeep | 10 |  | 0 | 70 | 0 | 70
CR Monitoring | PI22.1.3 CR monitoring [Gopal, Mohan] |  |  | 1 |  |  |  |  | Mohan | 10 |  | 1 | 63 | 0 | 63
[9 empty] | Vinay | 10 | 1 | 0 | 63 | 0 | 63
ITSM Validation | ITSM Validation |  |  | 12 |  |  |  |  | Himanshu | 10 |  | 0 | 70 | 0 | 70
[9 empty] | Sourav | 10 | 1 | 0 | 63 | 0 | 63
| Validation - N05 Call recording data migration to ASC |  |  | 2 |  |  |  |  | Jyoti | 3 |  | 0 | 21 | 0 | 21
| Client - Support MiCloud Connect SMS to 988 Feature validation |  |  | 2 |  |  |  |  | Total | 93 | 4.5 | 1 | 591.5 | 0 | 591.5
KT Sessions | KT and Learning Sessions |  |  | 5 |  |  |  |  | Total Story Points | 93 | 4.5 | 1 | 84.5 | 0
Auditing for the NewRelic monitoring | Initial discussions and documentation |  |  | 3 |  |  |  |  | Buffer (15%) | 12.675
ECC Decomision | ECC decomission Discussions & Test plan preparation |  |  | 2 |  |  |  |  | ITSM(15%) | 12.675 |  | Start Date | 2022-03-31
IM Server Decomission | IM server decomission discussions & test plan preparation |  |  | 1 |  |  |  |  | Project Support(5%) | 4.225 |  | End Date | 2022-04-13
| Automation documentation |  |  | 2 |  |  |  |  | Unplanned(15%) | 12.675
[9 empty] | Automation(40%) | 33.8
Automation | Python 3.9 Framework Testing |  |  | 7 |  | In Progress | Gopal / Sandeep |  | Learnings (10%) | 8.45
| CR data comparison tool |  |  | 5 |  |  | Asim / Sandeep |  | Planned Valocity | 71.825
| Trunk Switch Valdaiton |  |  | 5 |  | In Progress | Asim / Mohan
| Synthetics tests and integration with NR |  |  | 8 |  |  | Prasanna / Hardik
| Raybaum configuration automation |  |  | 1 |  | In Progress | Sandeep / Vinay
| SBC Migration |  |  | 1
| Automation Migration |  |  | 3
| Phone Switch validation |  |  | 5 |  | Done |  |  | Sandeep, Vinay (T1)
| Dashboard setup for Monitoring |  |  | 3 |  |  | Prasanna / Hardik |  | Gopal, Mohan (T2),
| Raybaum Address validation with Iq |  |  | 2 |  |  | Sandeep |  | Prasanna, Sourav ,
| Sky Phone Automation |  |  | 2 |  |  |  |  | Hardik, Asim (T4),
| CSV Optimization |  |  | 2 |  | In Progress | Prasanna / Hardik
| OCOM API for Voice Validation |  |  | 5 |  |  | Himanshu / Sourav
| Call Recording Automation Fix |  |  | 1 |  |  | Gopal
| RTP Engine & Turn Server Automation |  |  | 7 |  | In Progress | Sandeep
1
2
| Encrypt Password in CallRecordingCluster table Jira #: SBOSS-37030 |  |  | 1
| Encrypt Password in device_router table Jira #: SBOSS-37032 |  |  | 1
| Encrypt Password in ShoretelMobilityProfile table Jira #: SBOSS-37039 |  |  | 1
| Encrypt Password in ECCCluster table Jira #: SBOSS-37033 |  |  | 1

## PI22.1.4
Epic | Story | JiRA ID | Subtask | Efforts in SP | Spent | Remarks | Owner | account_id | Name | Number of working days | Leaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[9 empty] | Asim | 9 | 2 | 1 | 42 | 0 | 42
[9 empty] | Hardik | 9 |  | 0 | 63 | 0 | 63
[9 empty] | Prasanna | 9 |  | 1 | 39.2 | 0 | 39.2
Unplanned Task | PI22.1.4 Unplanned Task |  |  | 7 |  |  |  |  | Gopal | 9 |  | 0 | 63 | 0 | 63
[9 empty] | Sandeep | 9 |  | 0 | 63 | 0 | 63
CR Monitoring | PI22.1.4 CR monitoring [Prasanna, Sourav] |  |  | 1 |  |  |  |  | Mohan | 9 |  | 0 | 63 | 0 | 63
[9 empty] | Vinay | 9 |  | 1 | 56 | 0 | 56
ITSM Validation | ITSM Validation |  |  | 17 |  | ASC migration and ECC decommission |  |  | Sourav | 9 | 1 | 0 | 56 | 0 | 56
[9 empty] | Jyoti | 3 |  | 0 | 21 | 0 | 21
[9 empty] | Total | 75 | 3 | 3 | 466.2 | 0 | 466.2
KT Sessions | KT and Learning Sessions |  |  | 17 |  |  |  |  | Total Story Points | 75 | 3 | 3 | 66.6 | 0
Auditing for the NewRelic monitoring | Auditing NewRelic Alerts and Policies |  |  | 3 |  |  | Prasanna |  | Admin Tasks (10%) | 6.66
ECC Decomision | ECC decomission Discussions & Test plan preparation |  |  | 1 |  |  |  |  | ITSM(25%) | 16.65 |  | Start Date | 2022-04-14
[9 empty] | Project Support(5%) | 3.33 |  | End Date | 2022-04-27
| Automation documentation |  |  | 1 |  |  |  |  | Unplanned(10%) | 6.66
[9 empty] | Automation(25%) | 16.65
Automation Framework Migration from Python 2 to Python 3 | CDR-BI |  |  | 1.5 |  |  | Gopal |  | Learnings (25%) | 16.65
| Automation Support Migration running job |  |  | 2 |  |  |  |  | Planned Valocity | 59.94
| AutomationFramework/Utils files |  |  | 2
Automation | Synthetics tests and integration with NR |  |  | 3 |  |  | Prasanna / Hardik
| CR data comparison tool |  |  | 2 |  |  | Asim / Sandeep
| Raybaum configuration automation |  |  | 3 |  | In Progress | Sandeep / Vinay
| Trunk Switch Valdaiton |  |  | 2 |  | In Progress | Asim / Mohan
Sandeep, Vinay (T1)
Gopal, Mohan (T2),
Prasanna, Sourav ,
Hardik, Asim (T4),
| Python 3.9 Framework Testing |  |  |  |  | In Progress | Gopal / Sandeep
| CR data comparison tool | [5 empty] | Asim / Sandeep
| Trunk Switch Valdaiton |  |  |  |  | In Progress | Asim / Mohan
| Synthetics tests and integration with NR | [5 empty] | Prasanna / Hardik
| Raybaum configuration automation |  |  |  |  | In Progress | Sandeep / Vinay
| Phone Switch validation |  |  |  |  | Done
| Dashboard setup for Monitoring | [5 empty] | Prasanna / Hardik
| Raybaum Address validation with Iq | [5 empty] | Sandeep
Sky Phone Automation
| CSV Optimization |  |  |  |  | In Progress | Prasanna / Hardik
| OCOM API for Voice Validation | [5 empty] | Himanshu / Sourav
| Call Recording Automation Fix | [5 empty] | Gopal
| RTP Engine & Turn Server Automation |  |  |  |  | In Progress | Sandeep
Encrypt Password in CallRecordingCluster table Jira #: SBOSS-37030
Encrypt Password in device_router table Jira #: SBOSS-37032
Encrypt Password in ShoretelMobilityProfile table Jira #: SBOSS-37039
Encrypt Password in ECCCluster table Jira #: SBOSS-37033

## PI22.2 Backlogs
Portfolio Epic | Epic | Story | Sprint (the story is taken up) | Remarks | Dependencies
CP-15 [Micloud Connect & Sky: Service Observability]
UGV-7482 [GCO Validation Synthetics Monitoring]
Raybaum Synthetics Monitoring Sprint 22.2.1
Raybaum Synthetics Monitoring Sprint 22.2.2
Raybaum Synthetics Monitoring Sprint 22.2.3
Raybaum Synthetics Monitoring Sprint 22.2.4
CR Synthetics Monitoring Sprint 22.2.1
CR Synthetics Monitoring Sprint 22.2.2
CR Synthetics Monitoring Sprint 22.2.3
CR Synthetics Monitoring Sprint 22.2.4
LDVS Synthetics Monitoring Sprint 22.2.1
LDVS Synthetics Monitoring Sprint 22.2.2
LDVS Synthetics Monitoring Sprint 22.2.3
LDVS Synthetics Monitoring Sprint 22.2.4
UGV-7064 [GCO Validation Automation]
Synthetics monitoring integration with NR
|  | Trunk Switch Valdaiton |  | Blocked | OCOM portal access and API key
Raybaum Configuration automation
|  | Raybaum Address validation with Iq |  | Blocked
OCOM API for Voice Validation
CSV Optimization
|  | Sky Phone Automation |  | Blocked | SSH key issues
Dashboard setup for Monitoring
RTP Engine & Turn Server Automation
Global Number (python 3.9 migration)
Global User (python 3.9 migration)
HighBall (ECC) (python 3.9 migration)
HybridSites (python 3.9 migration)
Lync (python 3.9 migration)
SF (python 3.9 migration)
Telstrat-CR (python 3.9 migration)
SBC (python 3.9 migration)
|  | D&M (python 3.9 migration) |  | Blocked | Due to Jumpbox restrictions
BOSS (python 3.9 migration)
smc Automation (Python 3.9 migration)
3rd Party SBC validation through automation
69xx Phone Registration through Automation
UGV-7383 [Auditing NR Alerts (Monitoring)]
Test Plan for NR Alert Audit Sprint 22.2.1
Audit for all NR alert policies for Infra PBX Sprint 22.2.1
Audit for all NR alert policies for Services PBX Sprint 22.2.1
Audit for all NR alert policies for Usecase PBX Sprint 22.2.1
Test Plan for NR Alert Audit Sprint 22.2.2
Audit for all NR alert policies for Infra PBX Sprint 22.2.2
Audit for all NR alert policies for Services PBX Sprint 22.2.2
Audit for all NR alert policies for Usecase PBX Sprint 22.2.2
Audit for all NR alert policies for Infra ECC
Audit for all NR alert policies for Services ECC
Audit for all NR alert policies for Usecase ECC
|  | Audit for all NR alert policies for UCB |  | 3 subtasks for Infra, Service and Usecase
Audit for all NR alert policies for Fax & Scribe
Audit for all NR alert policies for Log Servers & Image Server
Test Plan for NR Alert Audit Sprint 22.2.3
Audit for all NR alert policies for BOSS
Audit for all NR alert policies for SBC
Audit for all NR alert policies for RTP Engine
Audit for all NR alert policies for ABC
Audit for all NR alert policies for Reverse Proxy
Audit for all NR alert policies for TURN and STUN
Test Plan for NR Alert Audit Sprint 22.2.4
Audit for all NR alert policies for Connect Client
Audit for all NR alert policies for Call Recording
Audit for all NR alert policies for NGDS
Audit for all NR alert policies for Raybaum
Audit for all NR alert policies for Mobility
CP-24 [Ongoing Support - Connect Client, Phone compatibility, Etc.]
| UGV-7480 [GCO ITSM Validation] | ITSM Validations Sprint 22.2.1
ITSM Validations Sprint 22.2.2
ITSM Validations Sprint 22.2.3
ITSM Validations Sprint 22.2.4
| UGV-7481 [GCO Validation Unplanned Tasks] | INC and unplanned tasks Sprint 22.2.1
INC and unplanned tasks Sprint 22.2.2
INC and unplanned tasks Sprint 22.2.3
INC and unplanned tasks Sprint 22.2.4
|  | ABC Rocky Linux |  |  | Need to discuss with the SRE team on detailed scope
CP-32[MiCloud Connect: ASC Data Migration and Telstrat Decom]
UGV-7447 [Validation for Telestrat - ASC Data Migration]
Validation of ASC Data Migration for AXL
Validation of ASC Data Migration for IDA
Validation of ASC Data Migration for N08
Validation of ASC Data Migration for N09
Validation of ASC Data Migration for N10
Validation of ASC Data Migration for TOM
|  | Validation of ASC Data Migration for URI |  | Completed - check with SRE
Validation of ASC Data Migration for ZED
|  | Validation of ASC Data Migration for N05 |  | In Progress
|  | Validation of ASC Data Migration for WES |  | In Progress
|  | Validation of ASC Data Migration for N11 |  | In Progress
Validation of Telstrat Decommissioning
CP-30 [Connect Service Consolidation & Capacity Management]
UGV-7449 [Validation for Services / Infra Decommissioning]
Validation of Decommisson of N08 ECC
Validation of Decommisson of N09 ECC
Validation of Decommisson of N10 ECC
|  | Validation of Decommison of AUS ECC ( VAL and A02) |  |  | Discussion with the SRE team on detailed plan
|  | Validation of Decommission of UK ECC (U01 and SID) |  |  | Discussion with the SRE team on detailed plan
Validation of Decommission of AXL ECC
Validation of Decommission of TOM ECC
Validation of Decommission of IDA ECC
Validation of Decommission of N05 ECC
Validation of Decommission of URI ECC
Validation of Decommission of N11 ECC
Validation of Decommission of WES ECC
Validation of Decommission of ZED ECC
Validation of Decommission of N14 ECC
Unused RC Decommission - ASC-1
Unused RC Decommission - ASC-2
Jfrog Decommissioning of non docker repos
Jfrog Infra Decommissioning
UGV-7382 [GCO Validation KT and Learning]
KT and Learning sessions Sprint 22.2.1
|  | KT and Learning sessions Sprint 22.2.2 |  | MS Team SBC Validation Understanding
KT and Learning sessions Sprint 22.2.3
KT and Learning sessions Sprint 22.2.4
Automation documentation Sprint 22.2.1
Automation documentation Sprint 22.2.2
Automation documentation Sprint 22.2.3
Automation documentation Sprint 22.2.4

## PI22.2.1
Portfolio Epic | Epic | Story | JiRA ID | Subtask | Efforts(SPs) | Spent | Remarks | Owner | account_id | Name | No of working days | PlannedLeaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[10 empty] | Asim | 9 | 1 |  | 44.8 | 0 | 44.8
CP-15 [Micloud Connect & Sky: Service Observability] | [9 empty] | Hardik | 9 |  |  | 63 | 0 | 63
| UGV-7482 [GCO Validation Synthetics Monitoring] | [8 empty] | Prasanna | 9 | 2.5 |  | 31.85 | 0 | 31.85
|  | Raybaum Synthetics Monitoring Sprint 22.2.1 |  |  | 1 |  |  |  |  | Gopal | 9 |  |  | 63 | 0 | 63
|  | CR Synthetics Monitoring Sprint 22.2.1 |  |  | 1 |  |  |  |  | Sandeep | 9 |  | 1 | 56 | 0 | 56
[10 empty] | Mohan | 9 | 1 |  | 56 | 0 | 56
| UGV-7064 [GCO Validation Automation] | [8 empty] | Vinay | 9 | 1 | 2 | 42 | 0 | 42
|  | Synthetics monitoring integration with NR |  |  | 2 |  |  | Hardik / Prasanna |  | Sourav | 9 | 1 |  | 56 | 0 | 56
|  | Global Number (python 3.9 migration) |  |  | 2 |  |  | Gopal |  | Jyoti | 2 |  |  | 14 | 0 | 14
|  | Global User (python 3.9 migration) |  |  | 2 |  |  | Gopal
|  | Raybaum Configuration automation |  |  | 1
[10 empty] | Total | 74 | 6.5 | 3 | 426.65 | 0 | 426.65
| UGV-7383 [Auditing NR Alerts (Monitoring)] | [8 empty] | Total Story Points | 74 | 6.5 | 3 | 60.95 | 0
|  | Test Plan for NR Alert Audit Sprint 22.2.1 |  |  | 5
|  | Audit for all NR alert policies for Infra PBX Sprint 22.2.1 |  |  | 4 |  | 1 Pod from GCP and GCVE respectively
|  | Audit for all NR alert policies for Services PBX Sprint 22.2.1 |  |  | 4
[10 empty] | Admin Tasks (10%) | 6.095
[10 empty] | ITSM(20%) | 12.19 |  | Start Date | 2022-04-28
CP-24 [Ongoing Support - Connect Client, Phone compatibility, Etc.] | [9 empty] | Project Support(35%) | 21.3325 |  | End Date | 2022-05-11
| UGV-7480 [GCO ITSM Validation] | [8 empty] | Unplanned(15%) | 9.1425
|  | ITSM Validations Sprint 22.2.1 |  |  | 12 |  |  |  |  | Automation(10%) | 6.095
| UGV-7481 [GCO Validation Unplanned Tasks] | [8 empty] | Learnings (10%) | 6.095
|  | INC and unplanned tasks Sprint 22.2.1 |  |  | 9 |  |  |  |  | Planned Valocity | 54.855
CP-32[MiCloud Connect: ASC Data Migration and Telstrat Decom]
UGV-7447 [Validation for Telestrat - ASC Data Migration]
|  | Validation for prod upgrade ASC1 |  |  | 1
|  | Validation for prod upgrade ASC2 |  |  | 1
|  | Validation of ASC Data Migration for N05 |  |  | 1 |  |  |  |  | Sandeep, Vinay (T1)
|  | Validation of ASC Data Migration for WES |  |  | 1 |  |  |  |  | Gopal, Mohan (T2),
|  | Validation of ASC Data Migration for N11 |  |  | 1 |  |  |  |  | Prasanna, Sourav ,
Hardik, Asim (T4),
CP-30 [Connect Service Consolidation & Capacity Management]
UGV-7449 [Validation for Services / Infra Decommissioning]
UGV-7382 [GCO Validation KT and Learning]
|  | KT and Learning sessions Sprint 22.2.1 |  |  | 5
|  | Automation documentation Sprint 22.2.1 |  |  | 2 |  | NR -Integration SBC Config | Prasanna Gopal
Note on M13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3rd May holiday

## PI22.2.2
Portfolio Epic | Epic | Story | JiRA ID | Subtask | Efforts(SPs) | Spent | Remarks | Owner | account_id | Name | No of working days | PlannedLeaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[10 empty] | Asim | 10 |  |  | 56 | 0 | 56
CP-15 [Micloud Connect & Sky: Service Observability] | [9 empty] | Hardik | 10 |  |  | 70 | 0 | 70
| UGV-7482 [GCO Validation Synthetics Monitoring] | [8 empty] | Prasanna | 10 | 2 | 0.5 | 36.75 | 0 | 36.75
|  | Raybaum Synthetics Monitoring Sprint 22.2.2 |  |  | 1 |  |  |  |  | Gopal | 10 | 1 |  | 63 | 0 | 63
|  | CR Synthetics Monitoring Sprint 22.2.2 |  |  | 1 |  |  |  |  | Sandeep | 10 |  |  | 70 | 0 | 70
[10 empty] | Mohan | 10 |  |  | 70 | 0 | 70
| UGV-7064 [GCO Validation Automation] | [8 empty] | Vinay | 10 |  |  | 70 | 0 | 70
|  | HighBall (ECC) (python 3.9 migration) |  |  | 3 |  | Selenium dependency |  |  | Sourav | 10 |  |  | 70 | 0 | 70
|  | SF (python 3.9 migration) |  |  | 1 |  |  |  |  | Jyoti | 3 |  |  | 21 | 0 | 21
|  | ASC-CR (python 3.9 migration) |  |  | 2
[10 empty] | Total | 83 | 3 | 0.5 | 526.75 | 0 | 526.75
| UGV-7383 [Auditing NR Alerts (Monitoring)] | [8 empty] | Total Story Points | 83 | 3 | 0.5 | 75.25 | 0
|  | Test Plan for NR Alert Audit Sprint 22.2.2 |  |  | 2 |  |  |  |  | Admin Tasks (10%) | 7.525
|  | Audit for all NR alert policies for Infra PBX Sprint 22.2.2 |  |  | 3 |  |  |  |  | ITSM(25%) | 18.8125 |  | Start Date | 2022-05-12
|  | Audit for all NR alert policies for Services PBX Sprint 22.2.2 |  |  | 3 |  |  |  |  | Project Support(30%) | 22.575 |  | End Date | 2022-05-25
[10 empty] | Unplanned(15%) | 11.2875
|  | Audit for all NR alert policies for Infra ECC |  |  | 3 |  |  |  |  | Automation(10%) | 7.525
|  | Audit for all NR alert policies for Services ECC |  |  | 3 |  |  |  |  | Learnings (10%) | 7.525
[10 empty] | Planned Valocity | 67.725
|  | Audit for all NR alert policies for UCB |  |  | 1 |  | 3 subtasks for Infra, Service and Usecase
|  | Audit for all NR alert policies for Fax & Scribe |  |  | 1 |  | 3 subtasks for Infra, Service and Usecase
|  | Audit for all NR alert policies for Log Servers & Image Server |  |  | 1 |  | 3 subtasks for Infra, Service and Usecase
CP-24 [Ongoing Support - Connect Client, Phone compatibility, Etc.]
| UGV-7480 [GCO ITSM Validation] | [8 empty] | Sandeep, Vinay (T1)
|  | ITSM Validations Sprint 22.2.2 | [7 empty] | Gopal, Mohan (T2),
| UGV-7481 [GCO Validation Unplanned Tasks] | [8 empty] | Prasanna, Sourav ,
|  | INC and unplanned tasks Sprint 22.2.2 |  |  | 11 |  |  |  |  | Hardik, Asim (T4),
CP-32[MiCloud Connect: ASC Data Migration and Telstrat Decom]
UGV-7447 [Validation for Telestrat - ASC Data Migration]
|  | Validation of ASC Data Migration for N09 |  |  | 1
|  | Validation of ASC Data Migration for N10 |  |  | 1
|  | Validation of ASC Data Migration for ZED |  |  | 1
|  | Validation Windows Security Patch on Prod ASC 1 servers |  |  | 1
CP-30 [Connect Service Consolidation & Capacity Management]
UGV-7449 [Validation for Services / Infra Decommissioning]
UGV-7382 [GCO Validation KT and Learning]
|  | KT and Learning sessions Sprint 22.2.2 |  |  | 5
|  | Automation documentation Sprint 22.2.2 |  |  | 2
CP-38 (UGV-7822) | FCC-988 | Understading the feature and meeting with other teams |  |  | 3
|  | Test plan preparation |  |  | 1

## PI22.2.3
Portfolio Epic | Epic | Story | JiRA ID | Subtask | Efforts(SPs) | Spent | Remarks | Owner | account_id | Name | No of working days | PlannedLeaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[10 empty] | Asim | 10 | 2 |  | 44.8 | 0 | 44.8
CP-15 [Micloud Connect & Sky: Service Observability] | [9 empty] | Hardik | 10 |  |  | 70 | 0 | 70
| UGV-7482 [GCO Validation Synthetics Monitoring] | [8 empty] | Prasanna | 10 |  |  | 49 | 0 | 49
|  | Raybaum Synthetics Monitoring Sprint 22.2.3 |  |  | 1 |  |  |  |  | Gopal | 10 | 1 |  | 63 | 0 | 63
|  | CR Synthetics Monitoring Sprint 22.2.3 |  |  | 1 |  |  |  |  | Sandeep | 10 |  |  | 70 | 0 | 70
[10 empty] | Mohan | 10 | 2 |  | 56 | 0 | 56
| UGV-7064 [GCO Validation Automation] | [8 empty] | Vinay | 10 |  |  | 70 | 0 | 70
|  | RTP Engine & Turn Server Automation |  |  | 3 |  |  |  |  | Sourav | 10 |  |  | 70 | 0 | 70
|  | Synthetics monitoring integration with NR |  |  | 1 |  | For Raybaum |  |  | Jyoti | 3 |  |  | 21 | 0 | 21
|  | CSV Optimization |  |  | 2
|  | SBC Automation Migration |  |  | 1
|  | Automation Framework Migration |  |  | 3 |  |  |  |  | Total | 83 | 5 | 0 | 513.8 | 0 | 513.8
| UGV-7383 [Auditing NR Alerts (Monitoring)] | [8 empty] | Total Story Points | 83 | 5 | 0 | 73.4 | 0
|  | Test Plan for NR Alert Audit Sprint 22.2.3 |  |  | 2 |  |  |  |  | Admin Tasks (10%) | 7.34
|  | Audit for all NR alert policies for BOSS |  |  | 3 |  | 3 subtasks for Infra, Service and Usecase |  |  | ITSM(25%) | 18.35 |  | Start Date | 2022-05-26
|  | Audit for all NR alert policies for SBC |  |  | 3 |  | 3 subtasks for Infra, Service and Usecase |  |  | Project Support(30%) | 22.02 |  | End Date | 2022-06-08
|  | Audit for all NR alert policies for RTP Engine |  |  | 2 |  | 3 subtasks for Infra, Service and Usecase |  |  | Unplanned(15%) | 11.01
|  | Audit for all NR alert policies for ABC |  |  | 2 |  | 3 subtasks for Infra, Service and Usecase |  |  | Automation(10%) | 7.34
|  | Audit for all NR alert policies for Reverse Proxy |  |  | 2 |  | 3 subtasks for Infra, Service and Usecase |  |  | Learnings (10%) | 7.34
|  | Audit for all NR alert policies for TURN and STUN |  |  | 2 |  | 3 subtasks for Infra, Service and Usecase |  |  | Planned Valocity | 66.06
CP-24 [Ongoing Support - Connect Client, Phone compatibility, Etc.]
| UGV-7480 [GCO ITSM Validation] | [8 empty] | Sandeep, Vinay (T1)
|  | ITSM Validations Sprint 22.2.3 | [7 empty] | Gopal, Mohan (T2),
| UGV-7481 [GCO Validation Unplanned Tasks] | [8 empty] | Prasanna, Sourav ,
|  | INC and unplanned tasks Sprint 22.2.3 |  |  | 11 |  |  |  |  | Hardik, Asim (T4),
CP-32[MiCloud Connect: ASC Data Migration and Telstrat Decom]
UGV-7447 [Validation for Telestrat - ASC Data Migration]
|  | Validation of ASC Data Migration for AXL |  |  | 2
|  | Validation of ASC Data Migration for IDA |  |  | 1
|  | Validation of ASC Data Migration for N08 |  |  | 1
CP-30 [Connect Service Consolidation & Capacity Management]
UGV-7449 [Validation for Services / Infra Decommissioning]
UGV-7382 [GCO Validation KT and Learning]
|  | KT and Learning sessions Sprint 22.2.3 |  |  | 5
|  | Automation documentation Sprint 22.2.3 |  |  | 2

## PI22.2.4
Portfolio Epic | Epic | Story | JiRA ID | Subtask | Efforts(SPs) | Spent | Remarks | Owner | account_id | Name | No of working days | PlannedLeaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[10 empty] | Asim | 10 | 3 |  | 39.2 | 0 | 39.2
CP-15 [Micloud Connect & Sky: Service Observability] | [9 empty] | Hardik | 10 | 1 |  | 63 | 0 | 63
| UGV-7482 [GCO Validation Synthetics Monitoring] | [8 empty] | Prasanna | 10 |  |  | 49 | 0 | 49
|  | Raybaum Synthetics Monitoring Sprint 22.2.4 |  |  | 1 |  |  |  |  | Gopal | 10 | 1 |  | 63 | 0 | 63
|  | CR Synthetics Monitoring Sprint 22.2.4 |  |  | 1 |  |  |  |  | Sandeep | 10 |  |  | 70 | 0 | 70
[10 empty] | Mohan | 10 |  |  | 70 | 0 | 70
| UGV-7064 [GCO Validation Automation] | [5 empty] | If we have some effort bandwidth then we'll take up some automation tasks |  |  | Vinay | 10 | 1 |  | 63 | 0 | 63
[10 empty] | Sourav | 10 | 1 |  | 63 | 0 | 63
[10 empty] | Jyoti | 3 |  |  | 21 | 0 | 21
[10 empty] | Total | 83 | 7 | 0 | 501.2 | 0 | 501.2
| UGV-7383 [Auditing NR Alerts (Monitoring)] | [8 empty] | Total Story Points | 83 | 7 | 0 | 71.6 | 0
[10 empty] | Admin Tasks (20%) | 14.32
|  | Audit for all NR alert policies for Connect Client |  |  |  |  | 3 subtasks for Infra, Service and Usecase |  |  | ITSM(25%) | 17.9 |  | Start Date | 2022-06-09
|  | Audit for all NR alert policies for Call Recording |  |  |  |  | 3 subtasks for Infra, Service and Usecase |  |  | Project Support(30%) | 21.48 |  | End Date | 2022-06-22
|  | Audit for all NR alert policies for NGDS |  |  |  |  | 3 subtasks for Infra, Service and Usecase |  |  | Unplanned(15%) | 10.74
|  | Audit for all NR alert policies for Raybaum |  |  |  |  | 3 subtasks for Infra, Service and Usecase |  |  | Automation(0%) | 0
|  | Audit for all NR alert policies for Mobility |  |  |  |  | 3 subtasks for Infra, Service and Usecase |  |  | Learnings (10%) | 7.16
[10 empty] | Planned Valocity | 57.28
CP-24 [Ongoing Support - Connect Client, Phone compatibility, Etc.]
| UGV-7480 [GCO ITSM Validation] | [8 empty] | Sandeep, Vinay (T1)
|  | ITSM Validations Sprint 22.2.4 | [7 empty] | Gopal, Mohan (T2),
| UGV-7481 [GCO Validation Unplanned Tasks] | [8 empty] | Prasanna, Sourav ,
|  | INC and unplanned tasks Sprint 22.2.4 |  |  | 11 |  |  |  |  | Hardik, Asim (T4),
CP-32[MiCloud Connect: ASC Data Migration and Telstrat Decom]
UGV-7447 [Validation for Telestrat - ASC Data Migration]
CP-30 [Connect Service Consolidation & Capacity Management]
UGV-7449 [Validation for Services / Infra Decommissioning]
UGV-7382 [GCO Validation KT and Learning]
|  | KT and Learning sessions Sprint 22.2.4 |  |  | 5
|  | Automation documentation Sprint 22.2.4 |  |  | 2

## PI22.3 Backlog
Portfolio Epic | Epic | Story | Sprint (the story is taken up) | Remarks | Dependencies
CP-15 [Micloud Connect & Sky: Service Observability]
UGV-8287 [GCO Validation Synthetics Monitoring 22.3]
|  | Raybaum Synthetics Monitoring Sprint 22.3.1 | 1
|  | Raybaum Synthetics Monitoring Sprint 22.3.2 | 1
|  | Raybaum Synthetics Monitoring Sprint 22.3.3 | 1
|  | Raybaum Synthetics Monitoring Sprint 22.3.4 | 1
Raybaum Synthetics Monitoring Sprint 22.3.5
|  | CR Synthetics Monitoring Sprint 22.3.1 | 1
|  | CR Synthetics Monitoring Sprint 22.3.2 | 1
|  | CR Synthetics Monitoring Sprint 22.3.3 | 1
|  | CR Synthetics Monitoring Sprint 22.3.4 | 1
CR Synthetics Monitoring Sprint 22.3.5
|  | LDVS Synthetics Monitoring Sprint 22.3.1 | 1
|  | LDVS Synthetics Monitoring Sprint 22.3.2 | 1
|  | LDVS Synthetics Monitoring Sprint 22.3.3 | 1
|  | LDVS Synthetics Monitoring Sprint 22.3.4 | 1
LDVS Synthetics Monitoring Sprint 22.3.5
UGV-8288 [GCO Validation Automation 22.3]
[Automation] LDVS synthetics monitoring suite set up
|  | [Automation] Synthetics monitoring integration with NR |  | Already done for CR and RayBaum. Need to discuss
|  | [Automation] Integration with NR to track the state of the Jenkins Nodes |  | IF there are issues with the test suite or the VM
|  | Raybaum Address validation with Iq |  | Blocked
|  | OCOM API for Voice Validation |  | Blocked
[Automation] CSV Optimization
|  | Sky Phone Automation |  | Blocked | SSH key issues (There can be some R&D in the upcoming IP iteration)
[Automation] Dashboard setup for Monitoring
[Automation] RTP Engine & Turn Server Automation
|  | [Automation] HybridSites (python 3.9 migration) |  |  | Need to check if the hybrid setup is still active and working
[Automation] Lync (python 3.9 migration)
|  | D&M (python 3.9 migration) |  | Blocked | Due to Jumpbox restrictions
[Automation] BOSS (python 3.9 migration)
|  | smc Automation (Python 3.9 migration) |  |  | No Automation scripts for SMR
[Automation] BOSS Automation script refinement
UGV-8289 [Auditing NR Alerts (Monitoring)- Defect Verification]
NR Alert audit Defect verification
CP-24 [Ongoing Support - Connect Client, Phone compatibility, Etc.]
| UGV-8290 [GCO ITSM Validation 22.3] | ITSM Validations Sprint 22.3.1
ITSM Validations Sprint 22.3.2
ITSM Validations Sprint 22.3.3
ITSM Validations Sprint 22.3.4
ITSM Validations Sprint 22.3.5
BOSS Upgrade support
| UGV-8291 [GCO Validation INC and Unplanned Tasks 22.3] | INC and unplanned tasks Sprint 22.3.1
INC and unplanned tasks Sprint 22.3.2
INC and unplanned tasks Sprint 22.3.3
INC and unplanned tasks Sprint 22.3.4
INC and unplanned tasks Sprint 22.3.5
CP-32[MiCloud Connect: ASC Data Migration and Telstrat Decom]
UGV-7447 [Validation for Telestrat - ASC Data Migration]
This will be moved to the next PI since many CR migration are in Impeded state
| UGV-8305 [Validation post ASC procedure to copy the CRs to new bucket] |  |  | Call recording validation after completing copying the records from buckets linked to decommissioned RMs
|  | Test case plan for moving CR recordings to new bucket |  |  | Saurav needs to refine the stories
Test case review for moving CR recordings to new bucket
Discussion with stakeholders for moving the ASC CR to new bucket
Validation of copied CRs to new bucket - ASC Cluster-1
Validation of copied CRs to new bucket - ASC Cluster-2
CP-30 [Connect Service Consolidation & Capacity Management]
UGV-8306 [Validation for Services / Infra Decommissioning 22.3]
Jfrog Decommissioning of non docker repos
Jfrog Infra Decommissioning
UGV-8307 [GCO Validation KT and Learning 22.3]
KT and Learning sessions Sprint 22.3.1
KT and Learning sessions Sprint 22.3.2
KT and Learning sessions Sprint 22.3.3
KT and Learning sessions Sprint 22.3.4
KT and Learning sessions Sprint 22.3.5
Automation documentation Sprint 22.3.1
Automation documentation Sprint 22.3.2
Automation documentation Sprint 22.3.3
Automation documentation Sprint 22.3.4
Automation documentation Sprint 22.3.5
CP-23 [MiCloud Connect and Sky: Platform Stability & Maintenance] |  |  |  | Discuss with PO (This will come as ITSMs)
CP-38 [FCC 988 Implementation]
| UGV-8076 [FCC-988 feature validation] | FCC-988 Test plan
FCC-988 Test plan Review and rework
FCC-988 feature test case execution
CP-22 [MiCloud Connect - Security / Compliance / Reliability]
| Encryption or removal of PIN and Password - BOSS feature |  |  | Discuss with PO | Discuss with BOSS team (This will come as ITSM)
CP-10 [MiCloud Connect: Current Hardware & OS Security Patch/Update Strategy & Implementation]
UGV-8308 [Validation of OS and security Patches upgrade]
|  | Discussion with other stackholders and Windows OS upgrade check point refinement |  |  | Sandeep
Windows OS upgrade detailed Test plan
Windows OS upgrade Test plan review and rework
Windows OS upgrade test case execution
| UGV-8309 [Validation of FireEye Installation] | FireEye AV installation
| UGV-8310 [Validation for Rocky Linux] | Rocky linux related validations
CP-21 [Stir Shaken]
| Validation of Stir Shaken |  |  | Need to discuss with the PO | Discuss with the comnet team. May come as ITSM

## PI22.3.1
Portfolio Epic | Epic | Story | JiRA ID | Subtask | Efforts(SPs) | Spent | Remarks | Owner | account_id | Name | No of working days | PlannedLeaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[10 empty] | Asim | 10 | 0 |  | 70 | 0 | 70
CP-15 [Micloud Connect & Sky: Service Observability] | [9 empty] | Hardik | 10 | 0 |  | 70 | 0 | 70
| UGV-7482 [GCO Validation Synthetics Monitoring] | [8 empty] | Prasanna | 10 | 1 |  | 44.1 | 0 | 44.1
[10 empty] | Gopal | 10 | 0 |  | 70 | 0 | 70
[10 empty] | Sandeep | 10 | 0 |  | 70 | 0 | 70
[10 empty] | Mohan | 10 | 0 |  | 70 | 0 | 70
| UGV-7064 [GCO Validation Automation] | [8 empty] | Vinay | 10 | 0 |  | 70 | 0 | 70
[10 empty] | Sourav | 10 | 2 |  | 56 | 0 | 56
[10 empty] | Total | 80 | 3 | 0 | 520.1 | 0 | 520.1
| UGV-7383 [Auditing NR Alerts (Monitoring)] | [8 empty] | Total Story Points | 80 | 3 | 0 | 74.3 | 0
[10 empty] | Admin Tasks (20%) | 14.86
[10 empty] | ITSM(25%) | 18.575 |  | Start Date | 2022-06-23
[10 empty] | Project Support(30%) | 22.29 |  | End Date | 2022-07-06
[10 empty] | Unplanned(15%) | 11.145
[10 empty] | Automation(0%) | 0
[10 empty] | Learnings (10%) | 7.43
[10 empty] | Planned Valocity | 59.44
CP-24 [Ongoing Support - Connect Client, Phone compatibility, Etc.]
| UGV-7480 [GCO ITSM Validation] | [8 empty] | Sandeep, Vinay (T1)
Gopal, Mohan (T2),
| UGV-7481 [GCO Validation Unplanned Tasks] | [8 empty] | Prasanna, Sourav ,
Hardik, Asim (T4),
CP-32[MiCloud Connect: ASC Data Migration and Telstrat Decom]
UGV-7447 [Validation for Telestrat - ASC Data Migration]
[14 empty] | itr -1 | itr -2 | itr -3 | itr -4 | itr -5
CP-30 [Connect Service Consolidation & Capacity Management] | [12 empty] | total | 58.6 | 54.6 | 59.6 | 42.6 | 53.6
| UGV-7449 [Validation for Services / Infra Decommissioning] | [11 empty] | ITSM(30%) | 17.58 | 16.38 | 17.88 | 12.78 | 10.72
[13 empty] | Project Support(30%) | 17.58 | 16.38 | 17.88 | 12.78
[13 empty] | Unplanned(20%) | 11.72 | 10.92 | 11.92 | 8.52 | 16.08
[13 empty] | Automation(10%) | 5.86 | 5.46 | 5.96 | 4.26
[13 empty] | Learnings (10%) | 5.86 | 5.46 | 5.96 | 4.26
UGV-7382 [GCO Validation KT and Learning]

## PI22.3.2
Portfolio Epic | Epic | Story | JiRA ID | Subtask | Efforts(SPs) | Spent | Remarks | Owner | account_id | Name | No of working days | PlannedLeaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[10 empty] | Asim | 10 | 0 |  | 70 | 0 | 70
CP-15 [Micloud Connect & Sky: Service Observability] | [9 empty] | Hardik | 10 | 1 |  | 63 | 0 | 63
| UGV-7482 [GCO Validation Synthetics Monitoring] | [8 empty] | Prasanna | 10 | 2 |  | 39.2 | 0 | 39.2
[10 empty] | Gopal | 10 | 2 |  | 56 | 0 | 56
[10 empty] | Sandeep | 10 | 0 |  | 70 | 0 | 70
[10 empty] | Mohan | 10 | 1 |  | 63 | 0 | 63
| UGV-7064 [GCO Validation Automation] | [8 empty] | Vinay | 10 | 1 |  | 63 | 0 | 63
[10 empty] | Sourav | 10 | 0 |  | 70 | 0 | 70
[10 empty] | Total | 80 | 7 | 0 | 494.2 | 0 | 494.2
| UGV-7383 [Auditing NR Alerts (Monitoring)] | [8 empty] | Total Story Points | 80 | 7 | 0 | 70.6 | 0
[10 empty] | Admin Tasks (20%) | 14.12
[10 empty] | ITSM(25%) | 17.65 |  | Start Date | 2022-07-07
[10 empty] | Project Support(30%) | 21.18 |  | End Date | 2022-07-20
[10 empty] | Unplanned(15%) | 10.59
[10 empty] | Automation(0%) | 0
[10 empty] | Learnings (10%) | 7.06
[10 empty] | Planned Valocity | 56.48
CP-24 [Ongoing Support - Connect Client, Phone compatibility, Etc.]
| UGV-7480 [GCO ITSM Validation] | [8 empty] | Sandeep, Vinay (T1)
Gopal, Mohan (T2),
| UGV-7481 [GCO Validation Unplanned Tasks] | [8 empty] | Prasanna, Sourav ,
Hardik, Asim (T4),
CP-32[MiCloud Connect: ASC Data Migration and Telstrat Decom]
UGV-7447 [Validation for Telestrat - ASC Data Migration]
CP-30 [Connect Service Consolidation & Capacity Management] | [11 empty] | total | 58.6
| UGV-7449 [Validation for Services / Infra Decommissioning] | [10 empty] | ITSM(30%) | 17.58
[12 empty] | Project Support(30%) | 17.58
[12 empty] | Unplanned(20%) | 11.72
[12 empty] | Automation(10%) | 5.86
[12 empty] | Learnings (10%) | 5.86
UGV-7382 [GCO Validation KT and Learning]

## PI22.3.3
Portfolio Epic | Epic | Story | JiRA ID | Subtask | Efforts(SPs) | Spent | Remarks | Owner | account_id | Name | No of working days | PlannedLeaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[10 empty] | Asim | 10 | 0 |  | 70 | 0 | 70
CP-15 [Micloud Connect & Sky: Service Observability] | [9 empty] | Hardik | 10 | 1 |  | 63 | 0 | 63
| UGV-7482 [GCO Validation Synthetics Monitoring] | [8 empty] | Prasanna | 10 | 0 |  | 49 | 0 | 49
[10 empty] | Gopal | 10 | 0 |  | 70 | 0 | 70
[10 empty] | Sandeep | 10 | 0 |  | 70 | 0 | 70
[10 empty] | Mohan | 10 | 0 |  | 70 | 0 | 70
| UGV-7064 [GCO Validation Automation] | [8 empty] | Vinay | 10 | 0 |  | 70 | 0 | 70
[10 empty] | Sourav | 10 | 1 |  | 63 | 0 | 63
[10 empty] | Total | 80 | 2 | 0 | 525 | 0 | 525
| UGV-7383 [Auditing NR Alerts (Monitoring)] | [8 empty] | Total Story Points | 80 | 2 | 0 | 75 | 0
[10 empty] | Admin Tasks (20%) | 15
[10 empty] | ITSM(25%) | 18.75 |  | Start Date | 2022-07-21
[10 empty] | Project Support(30%) | 22.5 |  | End Date | 2022-08-03
[10 empty] | Unplanned(15%) | 11.25
[10 empty] | Automation(0%) | 0
[10 empty] | Learnings (10%) | 7.5
[10 empty] | Planned Valocity | 60
CP-24 [Ongoing Support - Connect Client, Phone compatibility, Etc.]
| UGV-7480 [GCO ITSM Validation] | [8 empty] | Sandeep, Vinay (T1)
Gopal, Mohan (T2),
| UGV-7481 [GCO Validation Unplanned Tasks] | [8 empty] | Prasanna, Sourav ,
Hardik, Asim (T4),
CP-32[MiCloud Connect: ASC Data Migration and Telstrat Decom]
UGV-7447 [Validation for Telestrat - ASC Data Migration]
[12 empty] | total | 58.6
[12 empty] | ITSM(30%) | 17.58
CP-30 [Connect Service Consolidation & Capacity Management] | [11 empty] | Project Support(30%) | 17.58
| UGV-7449 [Validation for Services / Infra Decommissioning] | [10 empty] | Unplanned(20%) | 11.72
[12 empty] | Automation(10%) | 5.86
[12 empty] | Learnings (10%) | 5.86
UGV-7382 [GCO Validation KT and Learning]

## PI22.3.4
Portfolio Epic | Epic | Story | JiRA ID | Subtask | Efforts(SPs) | Spent | Remarks | Owner | account_id | Name | No of working days | PlannedLeaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[10 empty] | Asim | 8 | 0 |  | 44.8 | 0 | 44.8
CP-15 [Micloud Connect & Sky: Service Observability] | [9 empty] | Hardik | 8 | 0 |  | 56 | 0 | 56
| UGV-7482 [GCO Validation Synthetics Monitoring] | [8 empty] | Prasanna | 8 | 0 |  | 39.2 | 0 | 39.2
[10 empty] | Gopal | 8 | 0 |  | 56 | 0 | 56
[10 empty] | Sandeep | 8 | 0 |  | 56 | 0 | 56
[10 empty] | Mohan | 8 | 1 |  | 49 | 0 | 49
| UGV-7064 [GCO Validation Automation] | [8 empty] | Vinay | 8 | 1 |  | 49 | 0 | 49
[10 empty] | Sourav | 8 | 1 |  | 49 | 0 | 49
[10 empty] | Total | 64 | 3 | 0 | 399 | 0 | 399
| UGV-7383 [Auditing NR Alerts (Monitoring)] | [8 empty] | Total Story Points | 64 | 3 | 0 | 57 | 0
[10 empty] | Admin Tasks (20%) | 11.4
[10 empty] | ITSM(25%) | 14.25 |  | Start Date | 2022-08-04
[10 empty] | Project Support(30%) | 17.1 |  | End Date | 2022-08-17
[10 empty] | Unplanned(15%) | 8.55
[10 empty] | Automation(0%) | 0
[10 empty] | Learnings (10%) | 5.7
[10 empty] | Planned Valocity | 45.6
CP-24 [Ongoing Support - Connect Client, Phone compatibility, Etc.]
| UGV-7480 [GCO ITSM Validation] | [8 empty] | Sandeep, Vinay (T1)
Gopal, Mohan (T2),
| UGV-7481 [GCO Validation Unplanned Tasks] | [8 empty] | Prasanna, Sourav ,
Hardik, Asim (T4),
CP-32[MiCloud Connect: ASC Data Migration and Telstrat Decom]
UGV-7447 [Validation for Telestrat - ASC Data Migration]
CP-30 [Connect Service Consolidation & Capacity Management]
UGV-7449 [Validation for Services / Infra Decommissioning]
UGV-7382 [GCO Validation KT and Learning]

## PI22.3.5
Portfolio Epic | Epic | Story | JiRA ID | Subtask | Efforts(SPs) | Spent | Remarks | Owner | account_id | Name | No of working days | PlannedLeaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[10 empty] | Asim | 9 | 0 |  | 50.4 | 0 | 50.4
CP-15 [Micloud Connect & Sky: Service Observability]
| UGV-7482 [GCO Validation Synthetics Monitoring] | [8 empty] | Prasanna | 9 | 0 |  | 44.1 | 0 | 44.1
[10 empty] | Sandeep | 9 | 0 |  | 63 | 0 | 63
[10 empty] | Mohan | 9 | 0 |  | 63 | 0 | 63
[10 empty] | Vinay | 9 | 0 |  | 63 | 0 | 63
| UGV-7064 [GCO Validation Automation] | [8 empty] | Sourav | 9 | 0 |  | 63 | 0 | 63
[10 empty] | Total | 54 | 0 | 0 | 346.5 | 0 | 346.5
| UGV-7383 [Auditing NR Alerts (Monitoring)] | [8 empty] | Total Story Points | 54 | 0 | 0 | 49.5 | 0
[10 empty] | Admin Tasks (20%) | 9.9
[10 empty] | ITSM(25%) | 12.375 |  | Start Date | 2022-08-18
[10 empty] | Project Support(30%) | 14.85 |  | End Date | 2022-08-31
[10 empty] | Unplanned(15%) | 7.425
[10 empty] | Automation(0%) | 0
[10 empty] | Learnings (10%) | 4.95
[10 empty] | Planned Valocity | 39.6
CP-24 [Ongoing Support - Connect Client, Phone compatibility, Etc.]
| UGV-7480 [GCO ITSM Validation] | [8 empty] | Sandeep, Vinay (T1)
Gopal, Mohan (T2),
| UGV-7481 [GCO Validation Unplanned Tasks] | [8 empty] | Prasanna, Sourav ,
Hardik, Asim (T4),
CP-32[MiCloud Connect: ASC Data Migration and Telstrat Decom]
UGV-7447 [Validation for Telestrat - ASC Data Migration]
CP-30 [Connect Service Consolidation & Capacity Management]
UGV-7449 [Validation for Services / Infra Decommissioning]
UGV-7382 [GCO Validation KT and Learning]

## PI22.3.6
Portfolio Epic | Epic | Story | JiRA ID | Subtask | Efforts(SPs) | Spent | Remarks | Owner | account_id | Name | No of working days | PlannedLeaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[10 empty] | Asim | 9 | 1 |  | 44.8 | 0 | 44.8
CP-15 [Micloud Connect & Sky: Service Observability]
| UGV-7482 [GCO Validation Synthetics Monitoring] | [8 empty] | Prasanna | 9 | 0 | 1 | 39.2 | 0 | 39.2
[10 empty] | Sandeep | 9 | 0 | 1 | 56 | 0 | 56
[10 empty] | Mohan | 9 | 1 |  | 56 | 0 | 56
| UGV-7064 [GCO Validation Automation] | [8 empty] | Vinay | 9 | 0 | 1 | 56 | 0 | 56
[10 empty] | Sourav | 9 | 0 |  | 63 | 0 | 63
[10 empty] | Total | 54 | 2 | 3 | 315 | 0 | 315
| UGV-7383 [Auditing NR Alerts (Monitoring)] | [8 empty] | Total Story Points | 54 | 2 | 3 | 45 | 0
[10 empty] | Admin Tasks (20%) | 9
[10 empty] | ITSM(25%) | 11.25 |  | Start Date | 2022-09-01
[10 empty] | Project Support(30%) | 13.5 |  | End Date | 2022-09-14
[10 empty] | Unplanned(15%) | 6.75
[10 empty] | Automation(0%) | 0
[10 empty] | Learnings (10%) | 4.5
[10 empty] | Planned Valocity | 36
CP-24 [Ongoing Support - Connect Client, Phone compatibility, Etc.]
| UGV-7480 [GCO ITSM Validation] | [8 empty] | Sandeep, Vinay (T1)
Gopal, Mohan (T2),
| UGV-7481 [GCO Validation Unplanned Tasks] | [8 empty] | Prasanna, Sourav ,
Hardik, Asim (T4),
CP-32[MiCloud Connect: ASC Data Migration and Telstrat Decom]
UGV-7447 [Validation for Telestrat - ASC Data Migration]
CP-30 [Connect Service Consolidation & Capacity Management]
UGV-7449 [Validation for Services / Infra Decommissioning]
UGV-7382 [GCO Validation KT and Learning]

## PI22.3.7
Portfolio Epic | Epic | Story | JiRA ID | Subtask | Efforts(SPs) | Spent | Remarks | Owner | account_id | Name | No of working days | PlannedLeaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[10 empty] | Asim | 10 | 1 |  | 50.4 | 0 | 50.4
CP-15 [Micloud Connect & Sky: Service Observability]
| UGV-7482 [GCO Validation Synthetics Monitoring] | [8 empty] | Prasanna | 10 | 0 |  | 49 | 0 | 49
[10 empty] | Sandeep | 10 | 0 |  | 70 | 0 | 70
[10 empty] | Mohan | 10 | 0 |  | 70 | 0 | 70
| UGV-7064 [GCO Validation Automation] | [8 empty] | Vinay | 10 | 2 |  | 56 | 0 | 56
[10 empty] | Sourav | 10 | 1 |  | 63 | 0 | 63
[10 empty] | Total | 60 | 4 | 0 | 358.4 | 0 | 358.4
| UGV-7383 [Auditing NR Alerts (Monitoring)] | [8 empty] | Total Story Points | 60 | 4 | 0 | 51.2 | 0
[10 empty] | Admin Tasks (20%) | 10.24
[10 empty] | ITSM(25%) | 12.8 |  | Start Date | 2022-09-15
[10 empty] | Project Support(30%) | 15.36 |  | End Date | 2022-09-28
[10 empty] | Unplanned(15%) | 7.68
[10 empty] | Automation(0%) | 0
[10 empty] | Learnings (10%) | 5.12
[10 empty] | Planned Valocity | 40.96
CP-24 [Ongoing Support - Connect Client, Phone compatibility, Etc.]
| UGV-7480 [GCO ITSM Validation] | [8 empty] | Sandeep, Vinay (T1)
Gopal, Mohan (T2),
| UGV-7481 [GCO Validation Unplanned Tasks] | [8 empty] | Prasanna, Sourav ,
Hardik, Asim (T4),
CP-32[MiCloud Connect: ASC Data Migration and Telstrat Decom]
UGV-7447 [Validation for Telestrat - ASC Data Migration]
CP-30 [Connect Service Consolidation & Capacity Management]
UGV-7449 [Validation for Services / Infra Decommissioning]
UGV-7382 [GCO Validation KT and Learning]

## PI22.3.8
Portfolio Epic | Epic | Story | JiRA ID | Subtask | Efforts(SPs) | Spent | Remarks | Owner | account_id | Name | No of working days | PlannedLeaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
CP-15 [Micloud Connect & Sky: Service Observability]
| UGV-7482 [GCO Validation Synthetics Monitoring] | [8 empty] | Prasanna | 9 | 0 | 1 | 39.2 | 0 | 39.2
[10 empty] | Sandeep | 9 | 0 | 1 | 56 | 0 | 56
[10 empty] | Mohan | 9 |  |  | 63 | 0 | 63
| UGV-7064 [GCO Validation Automation] | [8 empty] | Vinay | 9 | 0 | 1 | 56 | 0 | 56
[10 empty] | Sourav | 9 | 1 |  | 56 | 0 | 56
[10 empty] | Total | 45 | 1 | 3 | 270.2 | 0 | 270.2
| UGV-7383 [Auditing NR Alerts (Monitoring)] | [8 empty] | Total Story Points | 45 | 1 | 3 | 38.6 | 0
[10 empty] | Admin Tasks (20%) | 7.72
[10 empty] | ITSM(25%) | 9.65 |  | Start Date | 2022-09-29
[10 empty] | Project Support(30%) | 11.58 |  | End Date | 2022-10-12
[10 empty] | Unplanned(15%) | 5.79
[10 empty] | Automation(0%) | 0
[10 empty] | Learnings (10%) | 3.86
[10 empty] | Planned Valocity | 30.88
CP-24 [Ongoing Support - Connect Client, Phone compatibility, Etc.]
| UGV-7480 [GCO ITSM Validation] | [8 empty] | Sandeep, Vinay (T1)
Gopal, Mohan (T2),
| UGV-7481 [GCO Validation Unplanned Tasks] | [8 empty] | Prasanna, Sourav ,
Hardik, Asim (T4),
CP-32[MiCloud Connect: ASC Data Migration and Telstrat Decom]
UGV-7447 [Validation for Telestrat - ASC Data Migration]
CP-30 [Connect Service Consolidation & Capacity Management]
UGV-7449 [Validation for Services / Infra Decommissioning]
UGV-7382 [GCO Validation KT and Learning]

## PI22.3.9
Portfolio Epic | Epic | Story | JiRA ID | Subtask | Efforts(SPs) | Spent | Remarks | Owner | account_id | Name | No of working days | PlannedLeaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
CP-15 [Micloud Connect & Sky: Service Observability]
| UGV-7482 [GCO Validation Synthetics Monitoring] | [8 empty] | Prasanna | 9 | 0 |  | 44.1 | 0 | 44.1
[10 empty] | Sandeep | 9 | 0 |  | 63 | 0 | 63
[10 empty] | Mohan | 9 | 0 |  | 63 | 0 | 63
| UGV-7064 [GCO Validation Automation] | [8 empty] | Vinay | 9 | 1 |  | 56 | 0 | 56
[10 empty] | Sourav | 9 | 0 |  | 63 | 0 | 63
[10 empty] | Total | 45 | 1 | 0 | 289.1 | 0 | 289.1
| UGV-7383 [Auditing NR Alerts (Monitoring)] | [8 empty] | Total Story Points | 45 | 1 | 0 | 41.3 | 0
[10 empty] | Admin Tasks (20%) | 8.26
[10 empty] | ITSM(25%) | 10.325 |  | Start Date | 2022-10-13
[10 empty] | Project Support(30%) | 12.39 |  | End Date | 2022-10-26
[10 empty] | Unplanned(15%) | 6.195
[10 empty] | Automation(0%) | 0
[10 empty] | Learnings (10%) | 4.13
[10 empty] | Planned Valocity | 33.04
CP-24 [Ongoing Support - Connect Client, Phone compatibility, Etc.]
| UGV-7480 [GCO ITSM Validation] | [8 empty] | Sandeep, Vinay (T1)
Gopal, Mohan (T2),
| UGV-7481 [GCO Validation Unplanned Tasks] | [8 empty] | Prasanna, Sourav ,
Hardik, Asim (T4),
CP-32[MiCloud Connect: ASC Data Migration and Telstrat Decom]
UGV-7447 [Validation for Telestrat - ASC Data Migration]
CP-30 [Connect Service Consolidation & Capacity Management]
UGV-7449 [Validation for Services / Infra Decommissioning]
UGV-7382 [GCO Validation KT and Learning]

## PI22.4 Backlog
Portfolio Epic | Epic | Story | Sprint (the story is taken up) | Remarks | Dependencies
CP-10 [Micloud Connect & Sky: Service Observability]
UGV-9779 [GCO Validation Synthetics Monitoring 22.4]
|  | Raybaum Synthetics Monitoring | 1
|  | CR Synthetics Monitoring | 1
|  | LDVS Synthetics Monitoring | 1
|  | CR Synthetics Monitoring (UK and AUS) |  | Need to be added to the synthetics
UGV-9781 [GCO Validation Automation 22.4]
|  | [Automation] Synthetics monitoring integration with NR |  | Already done for CR and RayBaum. Need to discuss
|  | Raybaum Address validation with Iq |  | Blocked
|  | OCOM API for Voice Validation |  | Blocked
[Automation] CSV Optimization
|  | Sky Phone Automation |  | Blocked | SSH key issues (There can be some R&D in the upcoming IP iteration)
[Automation] Dashboard setup for Monitoring
[Automation] RTP Engine & Turn Server Automation
[Automation] Lync (python 3.9 migration)
|  | D&M (python 3.9 migration) |  | Blocked | Due to Jumpbox restrictions
|  | smc Automation |  | Sanity suite needs to be developed in python 3.x
|  | [Automation] BOSS Automation script refinement |  | In-progress
|  | Overall automation code optimization, stabilization and refinements |  | In-Progress
Test suite exection in K8s cluster
MS Teams automation
Lab Phones setup stabilization, mapping and debugging
|  | RPRX certificate validation automation |  |  | High priority
CP-24 [Ongoing Support - Connect Client, Phone compatibility, Etc.]
| UGV-9783 [GCO ITSM Validation 22.4] | ITSM Validations
BOSS Upgrade support
| UGV-9784 [GCO Validation INC and Unplanned Tasks 22.4] | INC and unplanned tasks
| UGV-8307 [GCO Validation KT and Learning] |  |  | This EPIC will not have any parent portpolio epic from now
CP -101 Connect Rampdown
UGV-9827 [Validation for Services / Infra Decommissioning]
Test strategy for Telstrat Decommission for GCP
Test strategy for Decommission of PSBCs ( Centos -6)
Test strategy for Telstrat Decommission for GCVE
Test strategy for Decommission unused RM in Alpha - Part 1
Test strategy for Decommission unused RM in Alpha - Part 2
CP-107 [Connect Service monitoring and observability - Q4 Rollup]
| UGV-9782 [Auditing NR Alerts (Monitoring)- Defect Verification 22.4] |  |  | Move it under cp-101
NR Alert audit Defect verification
CP-32[MiCloud Connect: ASC Data Migration and Telstrat Decom]
| UGV-7447 [Validation for Telestrat - ASC Data Migration] |  |  |  | Completed
CP-30 [Connect Service Consolidation & Capacity Management]
| UGV-8306 [Validation for Services / Infra Decommissioning] |  |  | Discuss with PO (This will come as ITSMs)
Telstrat
SBC
Phone switch
UGV-8307 [GCO Validation KT and Learning]
KT and Learning sessions
Automation documentation
CP-23 [MiCloud Connect and Sky: Platform Stability & Maintenance]
CP-18 [Hippa Compliance]
CP-17 BOSS 82.4/5 - 69xx firmware – DHCP Support
CP-70 (GC0-84) : Rampdown / Decommission (Include Telstrat here), Switches, LDVS? Others GCO-58 – Check Other activities which we prioritized (NR audit, Log files shipping, Monitoring etc)

## PI22.4.1
Portfolio Epic | Epic | Story | JiRA ID | Subtask | Efforts(SPs) | Spent | Remarks | Owner | account_id | Name | No of working days | PlannedLeaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
[15 empty] | 0 | 0
CP-10 [Micloud Connect & Sky: Service Observability]
| UGV-9779 [GCO Validation Synthetics Monitoring 22.4] | [8 empty] | Prasanna | 10 | 0 |  | 49 | 0 | 49
[10 empty] | Sandeep | 10 | 0 |  | 70 | 0 | 70
[10 empty] | Mohan | 10 | 0 |  | 70 | 0 | 70
[10 empty] | Vinay | 10 | 0 |  | 70 | 0 | 70
| UGV-9781 [GCO Validation Automation 22.4] | [8 empty] | Sourav | 10 | 1 |  | 63 | 0 | 63
[10 empty] | Total | 50 | 1 | 0 | 322 | 0 | 322
| UGV-9782 [Auditing NR Alerts (Monitoring)- Defect Verification 22.4] | [8 empty] | Total Story Points | 50 | 1 | 0 | 46 | 0
[10 empty] | Admin Tasks (20%) | 9.2
[10 empty] | ITSM(25%) | 11.5 |  | Start Date | 2022-11-09
[10 empty] | Project Support(10%) | 4.6 |  | End Date | 2022-11-23
[10 empty] | Unplanned(15%) | 6.9
[10 empty] | Automation(20%) | 9.2
[10 empty] | Learnings (10%) | 4.6
[10 empty] | Planned Valocity | 36.8
CP-24 [Ongoing Support - Connect Client, Phone compatibility, Etc.]
| UGV-9783 [GCO ITSM Validation 22.4] | [8 empty] | Sandeep, Vinay (T1)
Gopal, Mohan (T2),
| UGV-9784 [GCO Validation INC and Unplanned Tasks 22.4] | [8 empty] | Prasanna, Sourav ,
UGV-8307 [GCO Validation KT and Learning]

## PI22.4.2
Portfolio Epic | Epic | Story | JiRA ID | Subtask | Efforts(SPs) | Spent | Remarks | Owner | account_id | Name | No of working days | PlannedLeaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
CP-15 [Micloud Connect & Sky: Service Observability]
| UGV-9779 [GCO Validation Synthetics Monitoring 22.4] | [8 empty] | Prasanna | 10 | 0 |  | 49 | 0 | 49
[10 empty] | Sandeep | 10 | 0 |  | 70 | 0 | 70
[10 empty] | Mohan | 10 | 0 |  | 70 | 0 | 70
[10 empty] | Vinay | 10 | 0 |  | 70 | 0 | 70
| UGV-9781 [GCO Validation Automation 22.4] | [8 empty] | Sourav | 10 | 0 |  | 70 | 0 | 70
[10 empty] | Total | 50 | 0 | 0 | 329 | 0 | 329
| UGV-9782 [Auditing NR Alerts (Monitoring)- Defect Verification 22.4] | [8 empty] | Total Story Points | 50 | 0 | 0 | 47 | 0
[10 empty] | Admin Tasks (20%) | 9.4
[10 empty] | ITSM(25%) | 11.75 |  | Start Date | 2022-11-24
[10 empty] | Project Support(10%) | 4.7 |  | End Date | 2022-12-08
[10 empty] | Unplanned(15%) | 7.05
[10 empty] | Automation(20%) | 9.4
[10 empty] | Learnings (10%) | 4.7
[10 empty] | Planned Valocity | 37.6
CP-24 [Ongoing Support - Connect Client, Phone compatibility, Etc.]
| UGV-9783 [GCO ITSM Validation 22.4] | [8 empty] | Sandeep, Vinay (T1)
Gopal, Mohan (T2),
| UGV-9784 [GCO Validation INC and Unplanned Tasks 22.4] | [8 empty] | Prasanna, Sourav ,
UGV-8307 [GCO Validation KT and Learning]

## PI22.4.3
Portfolio Epic | Epic | Story | JiRA ID | Subtask | Efforts(SPs) | Spent | Remarks | Owner | account_id | Name | No of working days | PlannedLeaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
CP-15 [Micloud Connect & Sky: Service Observability]
| UGV-9779 [GCO Validation Synthetics Monitoring 22.4] | [8 empty] | Prasanna | 16 | 0 |  | 78.4 | 0 | 78.4
[10 empty] | Sandeep | 16 | 2 |  | 98 | 0 | 98
[10 empty] | Mohan | 16 | 2 |  | 98 | 0 | 98
[10 empty] | Vinay | 4 | 0 |  | 28 | 0 | 28
| UGV-9781 [GCO Validation Automation 22.4] | [8 empty] | Sourav | 4 | 1 |  | 21 | 0 | 21
[10 empty] | Total | 56 | 5 | 0 | 323.4 | 0 | 323.4
| UGV-9782 [Auditing NR Alerts (Monitoring)- Defect Verification 22.4] | [8 empty] | Total Story Points | 56 | 5 | 0 | 46.2 | 0
[10 empty] | Admin Tasks (20%) | 9.24
[10 empty] | ITSM(25%) | 11.55 |  | Start Date | 2022-12-09
[10 empty] | Project Support(10%) | 4.62 |  | End Date | 2022-12-31
[10 empty] | Unplanned(15%) | 6.93
[10 empty] | Automation(20%) | 9.24
[10 empty] | Learnings (10%) | 4.62
[10 empty] | Planned Valocity | 36.96
CP-24 [Ongoing Support - Connect Client, Phone compatibility, Etc.]
| UGV-9783 [GCO ITSM Validation 22.4] | [8 empty] | Sandeep, Vinay (T1)
Gopal, Mohan (T2),
| UGV-9784 [GCO Validation INC and Unplanned Tasks 22.4] | [8 empty] | Prasanna, Sourav ,
UGV-8307 [GCO Validation KT and Learning]

## PI22.4 objectives
CP | Epic
CP-10 | UGV-9781 [GCO Validation Automation 22.4]
CP-101 | UGV-9827 [Validation for Services / Infra Decommissioning]
CP-24 | UGV-9783 [GCO ITSM Validation 22.4]
UGV-9782 [Auditing NR Alerts (Monitoring)- Defect Verification 22.4]
All Epics
CP-10 | UGV-9779 [GCO Validation Synthetics Monitoring 22.4]
CP-24 | UGV-9781 [GCO Validation Automation 22.4]
CP-101 | UGV-9783 [GCO ITSM Validation 22.4]
CP-107 | UGV-9784 [GCO Validation INC and Unplanned Tasks 22.4]
UGV-8307 [GCO Validation KT and Learning]
UGV-9827 [Validation for Services / Infra Decommissioning]
UGV-9782 [Auditing NR Alerts (Monitoring)- Defect Verification 22.4]

## PI23.1.1
Portfolio Epic | Epic | Story | JiRA ID | Subtask | Efforts(SPs) | Spent | Remarks | Owner | account_id | Name | No of working days | PlannedLeaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
CP-15 [Micloud Connect & Sky: Service Observability]
| UGV-9779 [GCO Validation Synthetics Monitoring 22.4] | [8 empty] | Prasanna | 10 | 0 |  | 49 | 0 | 49
[10 empty] | Sandeep | 10 | 0 |  | 70 | 0 | 70
[10 empty] | Mohan | 10 | 0 |  | 70 | 0 | 70
UGV-9781 [GCO Validation Automation 22.4]
[10 empty] | Total | 30 | 0 | 0 | 189 | 0 | 189
| UGV-9782 [Auditing NR Alerts (Monitoring)- Defect Verification 22.4] | [8 empty] | Total Story Points | 30 | 0 | 0 | 27 | 0
[10 empty] | Admin Tasks (20%) | 5.4
[10 empty] | ITSM(25%) | 4.05 |  | Start Date | 2023-01-02
[10 empty] | Project Support(10%) | 2.7 |  | End Date | 2023-01-13
[10 empty] | Unplanned(15%) | 4.05
[10 empty] | Automation(25%) | 6.75
[10 empty] | Learnings (15%) | 4.05
[10 empty] | Planned Valocity | 21.6
CP-24 [Ongoing Support - Connect Client, Phone compatibility, Etc.]
| UGV-9783 [GCO ITSM Validation 22.4] | [8 empty] | Sandeep, Vinay (T1)
Gopal, Mohan (T2),
| UGV-9784 [GCO Validation INC and Unplanned Tasks 22.4] | [8 empty] | Prasanna, Sourav ,
UGV-8307 [GCO Validation KT and Learning]

## PI23.1.2
Portfolio Epic | Epic | Story | JiRA ID | Subtask | Efforts(SPs) | Spent | Remarks | Owner | account_id | Name | No of working days | PlannedLeaves | EL | Total Effort (7h/d) | Planned Effort | Available Effort
CP-15 [Micloud Connect & Sky: Service Observability]
| UGV-9779 [GCO Validation Synthetics Monitoring 22.4] | [8 empty] | Prasanna | 10 | 0 |  | 49 | 0 | 49
[10 empty] | Sandeep | 10 | 0 |  | 70 | 0 | 70
[10 empty] | Mohan | 10 | 0 |  | 70 | 0 | 70
UGV-9781 [GCO Validation Automation 22.4]
[10 empty] | Total | 30 | 0 | 0 | 189 | 0 | 189
| UGV-9782 [Auditing NR Alerts (Monitoring)- Defect Verification 22.4] | [8 empty] | Total Story Points | 30 | 0 | 0 | 27 | 0
[10 empty] | Admin Tasks (20%) | 5.4
[10 empty] | ITSM(25%) | 4.05 |  | Start Date | 2023-01-18
[10 empty] | Project Support(10%) | 2.7 |  | End Date | 2023-02-01
[10 empty] | Unplanned(15%) | 4.05
[10 empty] | Automation(25%) | 6.75
[10 empty] | Learnings (15%) | 4.05
[10 empty] | Planned Valocity | 21.6
CP-24 [Ongoing Support - Connect Client, Phone compatibility, Etc.]
| UGV-9783 [GCO ITSM Validation 22.4] | [8 empty] | Sandeep, Vinay (T1)
Gopal, Mohan (T2),
| UGV-9784 [GCO Validation INC and Unplanned Tasks 22.4] | [8 empty] | Prasanna, Sourav ,
UGV-8307 [GCO Validation KT and Learning]

## Backlogs
UGV-2573 | UGV-3703 | [MCSS Automation] Huntgroup Creation | Asim
| UGV-3704 | [MCSS Automation] Huntgroup Fetch | Asim
| UGV-3705 | [MCSS Automation] Huntgroup Update | Asim
| UGV-3706 | [MCSS Automation] Huntgroup delete | Asim
UGV-2575 | UGV-3707 | [MCSS Automation] Autoattendent Creation | Asim
| UGV-3708 | [MCSS Automation] Autoattendent Fetch | Asim
| UGV-3709 | [MCSS Automation] Autoattendent Update | Asim
| UGV-3710 | [MCSS Automation] Autoattendent Delete | Asim
UGV-3696 | UGV-3711 | [MCSS Automation] Schedule Creation | Hardik
| UGV-3712 | [MCSS Automation] Schedule Fetch | Hardik
| UGV-3713 | [MCSS Automation] Schedule Update | Hardik
| UGV-3714 | [MCSS Automation] Schedule Delete | Hardik
UGV-3697 | UGV-3715 | [MCSS Automation] Extension Group Creation | Hardik
| UGV-3716 | [MCSS Automation] Extensiongroup Fetch | Hardik
| UGV-3717 | [MCSS Automation] Extensiongroup Update | Hardik
| UGV-3718 | [MCSS Automation] Extensiongroup Delete | Hardik

## Sheet2
Required For | Area | Task | Remarks | Priority | Status | Final Estimation
Leadership | Configuration | Instance Monitoring Setup |  | High | Started | 20
Leadership | Documentation | Documentation |  | High | Ongoing | 30
Team | Framework Enhancemet | Python 3.9 Framework Testing |  | Low | Ongoing | 30
Leadership |  | NewRelic and Jenkins Intigration | Only one of these need to be implemented | High | ToDo | 30
Team |  | Dashboard setup for Monitoring |  | High | ToDo | 20
Team |  | CSV Optimization |  | Medium | Ongoing | 10
Team |  | Call Recording Automation Fix |  | High | Ongoing | 10
Team |  | Cross Functional to Testing with Basic Call |  | Medium | Ongoing | 5
Team |  | Msteams basic calls with Browser |  | Low | ToDo | 20
Team |  | Jenkins Migration to Cent OS 8 |  | Low | ToDo | 10
|  | Automation Framework Setup on GCP |  |  | ToDo | 15
|  | Upgrade suite enhancement |  |  | ToDo | 5
|  | Chrome Driver Update |  |  | ToDo | 2
| Guidelines | Jenkins Failure ownership for monitoring |  |  | ToDo | 0
Migrate all VMs to GCP? redundancy
| Infra Enhancement | VM health Monitoring | New Relic can be used for this |  | ToDo | 5
|  | Phone Health Check |  |  | ToDo | 10
NOC | Instance Component | Phone Switch validation |  | High | Done | 5
NOC |  | Polycom Automation Registration |  | High | Ongoing | 20
NOC |  | Sky Phone Automation |  | High | Ongoing | 5
Team |  | Trunk Switch Valdaiton |  | Medium | ToDo | 15
New Feature | New Feature | Raybaum Address validation with Iq | Interliquent dependancy | High | Ongoing | 10
| Shared Component | ABC Automation |  |  | ToDo | 10
|  | TURN Automation |  |  | ToDo | 15
|  | RTP Engine Automation |  |  | ToDo | 15
|  | RP Automation |  |  | ToDo | 15
New Feature | Voice Validation | OCOM API for Voice Validation | DEPENDANCY | Medium | ToDo | 20
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: One of these two requirment will be developed